## Sheet 1
id;name;activity type;project;description;status;result;
6672;"Sign-off and send the approval for ""Optimix Go Live"" to Optimix Implementation team";"Implementation";"Select Medical - Implementation";"Sign-off and send the approval for ""Optimix Go Live"" to Optimix
Implementation team";"open";"";
6671;"Discuss with all the stake holders to get a joint confirmation readiness to Go Live in the Go No-go ";"Implementation";"Select Medical - Implementation";"Discuss with all the stake holders to get a joint confirmation
readiness to Go Live in the Go No-go call. Incase of a No-go need to
decide on the revised Go Live date and inform all the executive team
with valid reasons";"open";"";
6670;"Send the Go No Go call invitation to all the stake holders 5 days in advance ";"Implementation";"Select Medical - Implementation";"Send the Go No Go call invitation to all the stake holders 5 days in
advance";"open";"";
6669;"Work on Patches if any show stopper";"Implementation";"Select Medical - Implementation";"Work on Patches if any show stopper";"open";"";
6668;"List down the findings if any in the testing and share the same with Optimix Implementation team ";"Implementation";"Select Medical - Implementation";"List down the findings if any in the testing and share the same with
Optimix Implementation team";"open";"";
6667;"Select Medical Optimix users team start using IKS remote support service";"Implementation";"Select Medical - Implementation";"Select Medical Optimix users team start using IKS remote support
service";"open";"";
6666;"Sign-Off email in agreement on completion of IKS Optimix Implementation services and readiness to us";"Implementation";"Select Medical - Implementation";"Sign-Off email in agreement on completion of IKS Optimix
Implementation services and readiness to use IKS remote support
services";"open";"";
6665;"Discussion the transition from implementation services to remote support services. Elaborate the Sup";"Implementation";"Select Medical - Implementation";"Discussion the transition from implementation services to remote
support services. Elaborate the Support contact information
escalation metrics | support split up(Tier-1 | Tier-2 | etc.) and the
escalation metrics to Select Process Owners";"open";"";
6664;"Plan and setup a transition call between Select Process Owners | IKS Ops | and Remote support manager";"Implementation";"Select Medical - Implementation";"Plan and setup a transition call between Select Process Owners | IKS
Ops | and Remote support manager";"open";"";
6663;"Support team sign-off on the understanding of Knowledge transfer and documents shared by Optimix imp";"Implementation";"Select Medical - Implementation";"Support team sign-off on the understanding of Knowledge transfer and
documents shared by Optimix implementation team.";"open";"";
6662;"Fill and share the documents related to transition from implementation phase to remote support phase";"Implementation";"Select Medical - Implementation";"Fill and share the documents related to transition from implementation
phase to remote support phase during the knowledge sharing session.";"open";"";
6661;"Knowledge transfer on Select medical process | Operations strategy set-up in Optimix | Operations team";"Implementation";"Select Medical - Implementation";"Knowledge transfer on Select medical process | Operations strategy
set-up in Optimix | Operations team structure | Tasking flow | Open
issues and additional information to be shared.";"open";"";
6660;"Plan and setup the knowledge transfer call between IKS remote support manager | team lead | remote sup";"Implementation";"Select Medical - Implementation";"Plan and setup the knowledge transfer call between IKS remote support
manager | team lead | remote support team and Optimix Implementation
team.";"open";"";
6659;"Move To Remote Support ";"Implementation";"Select Medical - Implementation";"Move To Remote Support";"open";"";
6658;"Go Live";"Implementation";"Select Medical - Implementation";"Go Live";"open";"";
6657;"Roll out the email for completion of production environment setup";"Implementation";"Select Medical - Implementation";"Roll out the email for completion of production environment setup";"open";"";
6656;"sign-off on the testing and completion of patches";"Implementation";"Select Medical - Implementation";"sign-off on the testing and completion of patches";"open";"";
6655;"rectifying/testing patches if any Show Stopper";"Implementation";"Select Medical - Implementation";"rectifying/testing patches if any Show Stopper";"open";"";
6654;"Select Operations users working and testing the regular flow in Live environment with minimal data";"Implementation";"Select Medical - Implementation";"Select Operations users working and testing the regular flow in Live
environment with minimal data";"open";"";
6653;"Identify the Inventory for testing the live production site";"Implementation";"Select Medical - Implementation";"Identify the Inventory for testing the live production site";"open";"";
6652;"Prepare Live working scenarios based on current days Operation";"Implementation";"Select Medical - Implementation";"Prepare Live working scenarios based on current days Operation";"open";"";
6651;"Prepare the checklist for activities to be performed during testing ";"Implementation";"Select Medical - Implementation";"Prepare the checklist for activities to be performed during testing";"open";"";
6650;"Go Live Prep - Production Environment Testing";"Implementation";"Select Medical - Implementation";"Go Live Prep - Production Environment Testing";"open";"";
6649;"Smoke testing Patches if any Show Stopper";"Implementation";"Select Medical - Implementation";"Smoke testing Patches if any Show Stopper";"open";"";
6648;"Smoke Testing ";"Implementation";"Select Medical - Implementation";"Smoke Testing";"open";"";
6647;"IIS Setting Change for AD user ";"Implementation";"Select Medical - Implementation";"IIS Setting Change for AD user";"open";"";
6646;"Execute Rule Engine";"Implementation";"Select Medical - Implementation";"Execute Rule Engine";"open";"";
6645;"Reset Bucket and User for AR Encounters";"Implementation";"Select Medical - Implementation";"Reset Bucket and User for AR Encounters";"open";"";
6644;"Additional Data Import if any ";"Implementation";"Select Medical - Implementation";"Additional Data Import if any";"open";"";
6643;"Configure/Verify the Backup Schedule ";"Implementation";"Select Medical - Implementation";"Configure/Verify the Backup Schedule";"open";"";
6642;"Update the Web Config File in Production ";"Implementation";"Select Medical - Implementation";"Update the Web Config File in Production";"open";"";
6641;"Deploy the Code to Production Except Web Config";"Implementation";"Select Medical - Implementation";"Deploy the Code to Production Except Web Config";"open";"";
6640;"All Grouping configuration From UAT to PROD";"Implementation";"Select Medical - Implementation";"All Grouping configuration From UAT to PROD";"open";"";
6639;"Move Search Related Data from UAT to PROD";"Implementation";"Select Medical - Implementation";"Move Search Related Data from UAT to PROD";"open";"";
6638;"Move bucket Mapping Details from UAT to PROD";"Implementation";"Select Medical - Implementation";"Move bucket Mapping Details from UAT to PROD";"open";"";
6637;"Move Users Bucket From UAT to PROD";"Implementation";"Select Medical - Implementation";"Move Users Bucket From UAT to PROD";"open";"";
6636;"Move Users Data From UAT to PROD";"Implementation";"Select Medical - Implementation";"Move Users Data From UAT to PROD";"open";"";
6635;"Move Rule Engine Configuration From UAT to PROD ";"Implementation";"Select Medical - Implementation";"Move Rule Engine Configuration From UAT to PROD";"open";"";
6634;"Move Bucket Data from UAT to PROD";"Implementation";"Select Medical - Implementation";"Move Bucket Data from UAT to PROD";"open";"";
6633;"Execute Script to Create Indexes";"Implementation";"Select Medical - Implementation";"Execute Script to Create Indexes";"open";"";
6632;"Execute Alter Script for Data type Changes";"Implementation";"Select Medical - Implementation";"Execute Alter Script for Data type Changes";"open";"";
6631;"Execute Alter Script for Additional Columns";"Implementation";"Select Medical - Implementation";"Execute Alter Script for Additional Columns";"open";"";
6630;"Execute Create table Scripts";"Implementation";"Select Medical - Implementation";"Execute Create table Scripts";"open";"";
6629;"Take Production Code Backup ";"Implementation";"Select Medical - Implementation";"Take Production Code Backup";"open";"";
6628;"Take Production DB Backup.";"Implementation";"Select Medical - Implementation";"Take Production DB Backup.";"open";"";
6627;"Create Separate Folder for Upgrade activities";"Implementation";"Select Medical - Implementation";"Create Separate Folder for Upgrade activities";"open";"";
6626;"Bring down the live site in IIS";"Implementation";"Select Medical - Implementation";"Bring down the live site in IIS";"open";"";
6625;"Prepare the Checklist with the list activities Tobe performed for deployment ";"Implementation";"Select Medical - Implementation";"Prepare the Checklist with the list activities Tobe performed for
deployment";"open";"";
6624;"Go Live Prep - DB Migration and Masters Migration ";"Implementation";"Select Medical - Implementation";"Go Live Prep - DB Migration and Masters Migration";"open";"";
6623;"Deploy the migration in production";"Implementation";"Select Medical - Implementation";"Deploy the migration in production";"open";"";
6622;"Sign-Off on the data migration post completion of validation";"Implementation";"Select Medical - Implementation";"Sign-Off on the data migration post completion of validation";"open";"";
6621;"Validate the migrated data in the UAT server post deployment and execution of the migration scripts";"Implementation";"Select Medical - Implementation";"Validate the migrated data in the UAT server post deployment and
execution of the migration scripts";"open";"";
6620;"Testing of the migration scripts in the UAT Server ";"Implementation";"Select Medical - Implementation";"Testing of the migration scripts in the UAT Server";"open";"";
6619;"Deploy the migration scripts in the UAT server for testing";"Implementation";"Select Medical - Implementation";"Deploy the migration scripts in the UAT server for testing";"open";"";
6618;"Build the migration scripts based on the identified legacy data ";"Implementation";"Select Medical - Implementation";"Build the migration scripts based on the identified legacy data";"open";"";
6617;"Analyze and identify the legacy data that needs to be migrated to Optimix";"Implementation";"Select Medical - Implementation";"Analyze and identify the legacy data that needs to be migrated to
Optimix";"open";"";
6616;"Go Live Prep - Legacy Data Migration to Optimix";"Implementation";"Select Medical - Implementation";"Go Live Prep - Legacy Data Migration to Optimix";"open";"";
6614;"DARE Summary Report validation ";"Implementation";"Select Medical - Implementation";"DARE Summary Report validation";"open";"";
6613;"Tasking Detailed Report validation";"Implementation";"Select Medical - Implementation";"Tasking Detailed Report validation";"open";"";
6612;"Tasking Detailed Report validation";"Implementation";"Select Medical - Implementation";"Tasking Detailed Report validation";"open";"";
6611;"Tasking Summary Report validation";"Implementation";"Select Medical - Implementation";"Tasking Summary Report validation";"open";"";
6610;"Production Report validation";"Implementation";"Select Medical - Implementation";"Production Report validation";"open";"";
6609;"Activity Report validation ";"Implementation";"Select Medical - Implementation";"Activity Report validation";"open";"";
6608;"Other entities workorder activities - Tasking to other entities ";"Implementation";"Select Medical - Implementation";"Other entities workorder activities - Tasking to other entities";"open";"";
6607;"Other entities workorder activities - Task completion ";"Implementation";"Select Medical - Implementation";"Other entities workorder activities - Task completion";"open";"";
6606;"Other entities tasks allocation ";"Implementation";"Select Medical - Implementation";"Other entities tasks allocation";"open";"";
6605;"Other entities workorder activities - Tasking to other entities ";"Implementation";"Select Medical - Implementation";"Other entities workorder activities - Tasking to other entities";"open";"";
6604;"Other entities workorder activities - Task completion ";"Implementation";"Select Medical - Implementation";"Other entities workorder activities - Task completion";"open";"";
6603;"Other entities tasks allocation ";"Implementation";"Select Medical - Implementation";"Other entities tasks allocation";"open";"";
6602;"PP - Incoming tasks work flow ";"Implementation";"Select Medical - Implementation";"PP - Incoming tasks work flow";"open";"";
6601;"PP incoming tasks allocation ";"Implementation";"Select Medical - Implementation";"PP incoming tasks allocation";"open";"";
6600;"PP Work Order activities - Tasks over task and return task flow ";"Implementation";"Select Medical - Implementation";"PP Work Order activities - Tasks over task and return task flow";"open";"";
6599;"PP Work Order activities - Tasks Completion ";"Implementation";"Select Medical - Implementation";"PP Work Order activities - Tasks Completion";"open";"";
6598;"PP - Rejections Tasks Allocation";"Implementation";"Select Medical - Implementation";"PP - Rejections Tasks Allocation";"open";"";
6597;"Billing - Incoming tasks work flow ";"Implementation";"Select Medical - Implementation";"Billing - Incoming tasks work flow";"open";"";
6596;"Billing incoming tasks allocation ";"Implementation";"Select Medical - Implementation";"Billing incoming tasks allocation";"open";"";
6595;"Billing Work Order activities - Tasks over task and return task flow ";"Implementation";"Select Medical - Implementation";"Billing Work Order activities - Tasks over task and return task flow";"open";"";
6594;"Billing Work Order activities - Tasks Completion ";"Implementation";"Select Medical - Implementation";"Billing Work Order activities - Tasks Completion";"open";"";
6593;"Billing - Rejections Tasks Allocation";"Implementation";"Select Medical - Implementation";"Billing - Rejections Tasks Allocation";"open";"";
6592;"Denial Incoming tasks from Other entities ";"Implementation";"Select Medical - Implementation";"Denial Incoming tasks from Other entities";"open";"";
6591;"Denial incoming tasks work allocation";"Implementation";"Select Medical - Implementation";"Denial incoming tasks work allocation";"open";"";
6590;"Denial work order activities - Task to other entities ";"Implementation";"Select Medical - Implementation";"Denial work order activities - Task to other entities";"open";"";
6589;"Denial work order activities - Encounter completion ";"Implementation";"Select Medical - Implementation";"Denial work order activities - Encounter completion";"open";"";
6588;"Denial Work allocation ";"Implementation";"Select Medical - Implementation";"Denial Work allocation";"open";"";
6587;"AR Incoming tasks working from Other entities ";"Implementation";"Select Medical - Implementation";"AR Incoming tasks working from Other entities";"open";"";
6586;"AR incoming tasks work allocation";"Implementation";"Select Medical - Implementation";"AR incoming tasks work allocation";"open";"";
6585;"AR work order activities - Tasking to other entities and return task flow";"Implementation";"Select Medical - Implementation";"AR work order activities - Tasking to other entities and return task
flow";"open";"";
6584;"AR work order activities - Encounter completion ";"Implementation";"Select Medical - Implementation";"AR work order activities - Encounter completion";"open";"";
6583;"AR Work allocation ";"Implementation";"Select Medical - Implementation";"AR Work allocation";"open";"";
6582;"User Acceptance Test - Activities";"Implementation";"Select Medical - Implementation";"User Acceptance Test - Activities";"open";"";
6581;"Schedule the rejection import scripts in the UAT environment ";"Implementation";"Select Medical - Implementation";"Schedule the rejection import scripts in the UAT environment";"open";"";
6580;"Import of AR data from RT in UAT environment and scheduling the scripts for bringing in the delta da";"Implementation";"Select Medical - Implementation";"Import of AR data from RT in UAT environment and scheduling the
scripts for bringing in the delta data.";"open";"";
6579;"Rejection file import scripts to be deployed in the UAT process ";"Implementation";"Select Medical - Implementation";"Rejection file import scripts to be deployed in the UAT process";"open";"";
6578;"Data Import scripts deployment in the UAT environment";"Implementation";"Select Medical - Implementation";"Data Import scripts deployment in the UAT environment";"open";"";
6577;"UAT environment preparation and Optimix Deployment";"Implementation";"Select Medical - Implementation";"UAT environment preparation and Optimix Deployment";"open";"";
6576;"User Acceptance Test - Environment Setup and Data Import";"Implementation";"Select Medical - Implementation";"User Acceptance Test - Environment Setup and Data Import";"open";"";
6575;"Send an email confirmation to Optimix implementation team on the readiness for the UAT phase";"Implementation";"Select Medical - Implementation";"Send an email confirmation to Optimix implementation team on the
readiness for the UAT phase";"open";"";
6574;"Send the communication to all the select Optimix users on the start date of UAT | the activities to b";"Implementation";"Select Medical - Implementation";"Send the communication to all the select Optimix users on the start
date of UAT | the activities to be performed and the purpose of the UAT";"open";"";
6573;"Fix the resources and the inventory to work during the UAT phase";"Implementation";"Select Medical - Implementation";"Fix the resources and the inventory to work during the UAT phase";"open";"";
6572;"Discuss the plan with Select Process owners and explain the expectation the inventory and the resour";"Implementation";"Select Medical - Implementation";"Discuss the plan with Select Process owners and explain the
expectation the inventory and the resources to be available for UAT";"open";"";
6571;"Prepare and share the standard UAT plan to select process owners";"Implementation";"Select Medical - Implementation";"Prepare and share the standard UAT plan to select process owners";"open";"";
6570;"User Acceptance Test - Planning";"Implementation";"Select Medical - Implementation";"User Acceptance Test - Planning";"open";"";
6569;"Task responsibility detailed report to identify their respective clinics responsibility inventory an";"Implementation";"Select Medical - Implementation";"Task responsibility detailed report to identify their respective
clinics responsibility inventory and bifurcation of the tasks";"open";"";
6568;"Task Summary report extraction to identify their respective clinics pending/in progress tasks";"Implementation";"Select Medical - Implementation";"Task Summary report extraction to identify their respective clinics
pending/in progress tasks";"open";"";
6567;"Return task flow set-up in Optimix";"Implementation";"Select Medical - Implementation";"Return task flow set-up in Optimix";"open";"";
6566;"Tasking work order screen features";"Implementation";"Select Medical - Implementation";"Tasking work order screen features";"open";"";
6565;"Working on a task in Optimix";"Implementation";"Select Medical - Implementation";"Working on a task in Optimix";"open";"";
6564;"Tasking workflow set-up in Optimix";"Implementation";"Select Medical - Implementation";"Tasking workflow set-up in Optimix";"open";"";
6563;"Training to Clinics/RCM's";"Implementation";"Select Medical - Implementation";"Training to Clinics/RCM's";"open";"";
6562;"Looking in to individual hourly production";"Implementation";"Select Medical - Implementation";"Looking in to individual hourly production";"open";"";
6561;"Working on rejected tasks from a supervisor";"Implementation";"Select Medical - Implementation";"Working on rejected tasks from a supervisor";"open";"";
6560;"Working on incoming tasks inventory";"Implementation";"Select Medical - Implementation";"Working on incoming tasks inventory";"open";"";
6559;"Tasking from an encounter | working on return task";"Implementation";"Select Medical - Implementation";"Tasking from an encounter | working on return task";"open";"";
6558;"Completing an encounter/ task";"Implementation";"Select Medical - Implementation";"Completing an encounter/ task";"open";"";
6557;"Forwarding an encounter/ task";"Implementation";"Select Medical - Implementation";"Forwarding an encounter/ task";"open";"";
6556;"Features and functionalities on the work order screen ";"Implementation";"Select Medical - Implementation";"Features and functionalities on the work order screen";"open";"";
6555;"Training to Agents";"Implementation";"Select Medical - Implementation";"Training to Agents";"open";"";
6554;"Tasking responsibility detailed report extraction and interpretation";"Implementation";"Select Medical - Implementation";"Tasking responsibility detailed report extraction and interpretation";"open";"";
6553;"Tasking summary report extraction and interpretation";"Implementation";"Select Medical - Implementation";"Tasking summary report extraction and interpretation";"open";"";
6552;"Billing Production reports extraction and interpretation";"Implementation";"Select Medical - Implementation";"Billing Production reports extraction and interpretation";"open";"";
6551;"Activity and production reports extraction and interpretation";"Implementation";"Select Medical - Implementation";"Activity and production reports extraction and interpretation";"open";"";
6550;"Tasks approval | Rejection and voiding process";"Implementation";"Select Medical - Implementation";"Tasks approval | Rejection and voiding process";"open";"";
6549;"Tasking allocation and return task allocation";"Implementation";"Select Medical - Implementation";"Tasking allocation and return task allocation";"open";"";
6548;"Managing team leaders own workorder";"Implementation";"Select Medical - Implementation";"Managing team leaders own workorder";"open";"";
6547;"Managing teams workorder";"Implementation";"Select Medical - Implementation";"Managing teams workorder";"open";"";
6546;"Auto and Manual Tasks allocation | Inventory upload and deallocation of inventory";"Implementation";"Select Medical - Implementation";"Auto and Manual Tasks allocation | Inventory upload and deallocation of
inventory";"open";"";
6545;"Auto and Manual encounters allocation | Inventory upload and deallocation of inventory";"Implementation";"Select Medical - Implementation";"Auto and Manual encounters allocation | Inventory upload and
deallocation of inventory";"open";"";
6544;"Training to Team Leaders";"Implementation";"Select Medical - Implementation";"Training to Team Leaders";"open";"";
6543;"DARE Summary report extraction and interpretation";"Implementation";"Select Medical - Implementation";"DARE Summary report extraction and interpretation";"open";"";
6542;"how to perform Operations Shuffling";"Implementation";"Select Medical - Implementation";"how to perform Operations Shuffling";"open";"";
6541;"Interpretation of the Outstanding report ";"Implementation";"Select Medical - Implementation";"Interpretation of the Outstanding report";"open";"";
6540;"The exceptions considered while preparing the AR Operations strategy ";"Implementation";"Select Medical - Implementation";"The exceptions considered while preparing the AR Operations strategy";"open";"";
6539;"The AR non-workable logics setup in Optimix";"Implementation";"Select Medical - Implementation";"The AR non-workable logics setup in Optimix";"open";"";
6538;"Tasking workflow set-up for CBO";"Implementation";"Select Medical - Implementation";"Tasking workflow set-up for CBO";"open";"";
6537;"Current tasking workflow setup for Internal entities ";"Implementation";"Select Medical - Implementation";"Current tasking workflow setup for Internal entities";"open";"";
6536;"Current Operations strategy and rules set-up for billing workable inventory ";"Implementation";"Select Medical - Implementation";"Current Operations strategy and rules set-up for billing workable
inventory";"open";"";
6535;"Current Operations strategy and the AR workable inventory rules set-up and the process to follow in ";"Implementation";"Select Medical - Implementation";"Current Operations strategy and the AR workable inventory rules set-up
and the process to follow in case of changing the rules set";"open";"";
6534;"Training to Managers";"Implementation";"Select Medical - Implementation";"Training to Managers";"open";"";
6533;"Training Schedule to be prepared and calendar invites sent to Select users";"Implementation";"Select Medical - Implementation";"Training Schedule to be prepared and calendar invites sent to Select
users";"open";"";
6532;"Make the necessary infrastructure arrangements if required for the trainings to be conducted";"Implementation";"Select Medical - Implementation";"Make the necessary infrastructure arrangements if required for the
trainings to be conducted";"open";"";
6531;"Plan the mode of training for the 2 CBO users";"Implementation";"Select Medical - Implementation";"Plan the mode of training for the 2 CBO users";"open";"";
6530;"Plan the mode of training to be given to the clinic users";"Implementation";"Select Medical - Implementation";"Plan the mode of training to be given to the clinic users";"open";"";
6529;"Training plan drafted clearly calling out the modules | time date | mode of training and place of trai";"Implementation";"Select Medical - Implementation";"Training plan drafted clearly calling out the modules | time date | mode
of training and place of training";"open";"";
6528;"Training Plan and Scheduling";"Implementation";"Select Medical - Implementation";"Training Plan and Scheduling";"open";"";
6527;"Looking in to individual hourly production";"Implementation";"Select Medical - Implementation";"Looking in to individual hourly production";"open";"";
6526;"Working on rejected tasks from a supervisor";"Implementation";"Select Medical - Implementation";"Working on rejected tasks from a supervisor";"open";"";
6525;"Working on incoming tasks inventory";"Implementation";"Select Medical - Implementation";"Working on incoming tasks inventory";"open";"";
6524;"Tasking from an encounter | working on return task";"Implementation";"Select Medical - Implementation";"Tasking from an encounter | working on return task";"open";"";
6523;"Completing an encounter/ task";"Implementation";"Select Medical - Implementation";"Completing an encounter/ task";"open";"";
6522;"Forwarding an encounter/ task";"Implementation";"Select Medical - Implementation";"Forwarding an encounter/ task";"open";"";
6521;"Features and functionalities on the work order screen ";"Implementation";"Select Medical - Implementation";"Features and functionalities on the work order screen";"open";"";
6520;"To Perform Agents Activities";"Implementation";"Select Medical - Implementation";"To Perform Agents Activities";"open";"";
6519;"Tasking responsibility detailed report extraction and interpretation";"Implementation";"Select Medical - Implementation";"Tasking responsibility detailed report extraction and interpretation";"open";"";
6518;"Tasking summary report extraction and interpretation";"Implementation";"Select Medical - Implementation";"Tasking summary report extraction and interpretation";"open";"";
6517;"Rejection production reports extraction and interpretation";"Implementation";"Select Medical - Implementation";"Rejection production reports extraction and interpretation";"open";"";
6516;"Activity and production reports extraction and interpretation";"Implementation";"Select Medical - Implementation";"Activity and production reports extraction and interpretation";"open";"";
6515;"Tasks approval | Rejection and voiding process";"Implementation";"Select Medical - Implementation";"Tasks approval | Rejection and voiding process";"open";"";
6514;"Tasking allocation and return task allocation";"Implementation";"Select Medical - Implementation";"Tasking allocation and return task allocation";"open";"";
6513;"Managing team leaders own workorder";"Implementation";"Select Medical - Implementation";"Managing team leaders own workorder";"open";"";
6512;"Managing teams workorder";"Implementation";"Select Medical - Implementation";"Managing teams workorder";"open";"";
6511;"Auto and Manual Tasks allocation | Inventory upload and deallocation of inventory";"Implementation";"Select Medical - Implementation";"Auto and Manual Tasks allocation | Inventory upload and deallocation of
inventory";"open";"";
6510;"Auto and Manual encounters allocation | Inventory upload and deallocation of inventory";"Implementation";"Select Medical - Implementation";"Auto and Manual encounters allocation | Inventory upload and
deallocation of inventory";"open";"";
6509;"To Perform Team Leader Activities";"Implementation";"Select Medical - Implementation";"To Perform Team Leader Activities";"open";"";
6508;"DARE Summary report extraction and interpretation";"Implementation";"Select Medical - Implementation";"DARE Summary report extraction and interpretation";"open";"";
6507;"how to perform Operations Shuffling";"Implementation";"Select Medical - Implementation";"how to perform Operations Shuffling";"open";"";
6506;"Interpretation of the Outstanding report ";"Implementation";"Select Medical - Implementation";"Interpretation of the Outstanding report";"open";"";
6505;"The exceptions considered while preparing the AR Operations strategy ";"Implementation";"Select Medical - Implementation";"The exceptions considered while preparing the AR Operations strategy";"open";"";
6504;"The AR non-workable logics setup in Optimix";"Implementation";"Select Medical - Implementation";"The AR non-workable logics setup in Optimix";"open";"";
6503;"Tasking workflow set-up for CBO";"Implementation";"Select Medical - Implementation";"Tasking workflow set-up for CBO";"open";"";
6502;"Current tasking workflow setup for Internal entities ";"Implementation";"Select Medical - Implementation";"Current tasking workflow setup for Internal entities";"open";"";
6501;"Current Operations strategy and rules set-up for billing workable inventory ";"Implementation";"Select Medical - Implementation";"Current Operations strategy and rules set-up for billing workable
inventory";"open";"";
6500;"Current Operations strategy and the AR workable inventory rules set-up and the process to follow in ";"Implementation";"Select Medical - Implementation";"Current Operations strategy and the AR workable inventory rules set-up
and the process to follow in case of changing the rules set";"open";"";
6499;"Perform Administration/ Manager Activities";"Implementation";"Select Medical - Implementation";"Perform Administration/ Manager Activities";"open";"";
6498;"Give an Overall working demo on the product";"Implementation";"Select Medical - Implementation";"Give an Overall working demo on the product";"open";"";
6497;"Select trainer creates availability based on the schedule ";"Implementation";"Select Medical - Implementation";"Select trainer creates availability based on the schedule";"open";"";
6496;"Training Schedule to be prepared and calendar invites sent to Select users";"Implementation";"Select Medical - Implementation";"Training Schedule to be prepared and calendar invites sent to Select
users";"open";"";
6495;"Training plan drafted clearly with the sessions and topics to be trained on which day | date | Venue | ";"Implementation";"Select Medical - Implementation";"Training plan drafted clearly with the sessions and topics to be
trained on which day | date | Venue | and the respective audience";"open";"";
6494;"Plan for Training";"Implementation";"Select Medical - Implementation";"Plan for Training";"open";"";
6493;"Masters Validation";"Implementation";"Select Medical - Implementation";"Masters Validation";"open";"";
6492;"User Mapping validation";"Implementation";"Select Medical - Implementation";"User Mapping validation";"open";"";
6491;"Buckets Mapping validation ";"Implementation";"Select Medical - Implementation";"Buckets Mapping validation";"open";"";
6490;"Bucket validation";"Implementation";"Select Medical - Implementation";"Bucket validation";"open";"";
6489;"Rules Logic Validation";"Implementation";"Select Medical - Implementation";"Rules Logic Validation";"open";"";
6488;"Rules Logic Validation";"Implementation";"Select Medical - Implementation";"Rules Logic Validation";"open";"";
6487;"OS report validation";"Implementation";"Select Medical - Implementation";"OS report validation";"open";"";
6486;"OS Vs Ageing validation ";"Implementation";"Select Medical - Implementation";"OS Vs Ageing validation";"open";"";
6485;"Validation ";"Implementation";"Select Medical - Implementation";"Validation";"open";"";
6484;"User Mapping configuration - Clinics";"Implementation";"Select Medical - Implementation";"User Mapping configuration - Clinics";"open";"";
6483;"Tasking Buckets Mapping configuration - Clinics";"Implementation";"Select Medical - Implementation";"Tasking Buckets Mapping configuration - Clinics";"open";"";
6482;"Creation of Tasking Buckets - Clinics";"Implementation";"Select Medical - Implementation";"Creation of Tasking Buckets - Clinics";"open";"";
6481;"User Mapping configuration - Other Entities";"Implementation";"Select Medical - Implementation";"User Mapping configuration - Other Entities";"open";"";
6480;"Tasking Buckets Mapping configuration - Other Entities";"Implementation";"Select Medical - Implementation";"Tasking Buckets Mapping configuration - Other Entities";"open";"";
6479;"Creation of Tasking Buckets - Other Entities";"Implementation";"Select Medical - Implementation";"Creation of Tasking Buckets - Other Entities";"open";"";
6478;"User Mapping configuration - PP";"Implementation";"Select Medical - Implementation";"User Mapping configuration - PP";"open";"";
6477;"Tasking Buckets Mapping configuration - PP";"Implementation";"Select Medical - Implementation";"Tasking Buckets Mapping configuration - PP";"open";"";
6476;"Creation of Tasking Buckets - PP";"Implementation";"Select Medical - Implementation";"Creation of Tasking Buckets - PP";"open";"";
6475;"User Mapping configuration - Rejection Management";"Implementation";"Select Medical - Implementation";"User Mapping configuration - Rejection Management";"open";"";
6474;"Buckets Mapping configuration - Rejection Management ";"Implementation";"Select Medical - Implementation";"Buckets Mapping configuration - Rejection Management";"open";"";
6473;"Creation of rules - Rejection Management ";"Implementation";"Select Medical - Implementation";"Creation of rules - Rejection Management";"open";"";
6472;"Creation of Buckets - Rejection Management ";"Implementation";"Select Medical - Implementation";"Creation of Buckets - Rejection Management";"open";"";
6471;"User Mapping configuration - AR";"Implementation";"Select Medical - Implementation";"User Mapping configuration - AR";"open";"";
6470;"Buckets Mapping configuration - AR ";"Implementation";"Select Medical - Implementation";"Buckets Mapping configuration - AR";"open";"";
6469;"Creation of rules - AR ";"Implementation";"Select Medical - Implementation";"Creation of rules - AR";"open";"";
6468;"Creation of Buckets - AR ";"Implementation";"Select Medical - Implementation";"Creation of Buckets - AR";"open";"";
6467;"User Masters upload";"Implementation";"Select Medical - Implementation";"User Masters upload";"open";"";
6466;"Masters Data Configuration ";"Implementation";"Select Medical - Implementation";"Masters Data Configuration";"open";"";
6465;"Clinics Mapping: Location/Practice/Bucket";"Implementation";"Select Medical - Implementation";"Clinics Mapping: Location/Practice/Bucket";"open";"";
6464;"Tasking Buckets Mapping to Users - AR / Billing / PP / Other Entities";"Implementation";"Select Medical - Implementation";"Tasking Buckets Mapping to Users - AR / Billing / PP / Other Entities";"open";"";
6463;"Buckets Mapping to Users - AR / Billing / PP / Other Entities";"Implementation";"Select Medical - Implementation";"Buckets Mapping to Users - AR / Billing / PP / Other Entities";"open";"";
6462;"User Master - AR / Billing / PP / Other Entities";"Implementation";"Select Medical - Implementation";"User Master - AR / Billing / PP / Other Entities";"open";"";
6461;"Rejections Bucket Masters ";"Implementation";"Select Medical - Implementation";"Rejections Bucket Masters";"open";"";
6460;"Rejection Messages Groupings";"Implementation";"Select Medical - Implementation";"Rejection Messages Groupings";"open";"";
6459;"Rules Masters - Rejections";"Implementation";"Select Medical - Implementation";"Rules Masters - Rejections";"open";"";
6458;"Rules Masters - AR";"Implementation";"Select Medical - Implementation";"Rules Masters - AR";"open";"";
6457;"Denial Categorization groupings ";"Implementation";"Select Medical - Implementation";"Denial Categorization groupings";"open";"";
6456;"Buckets Master";"Implementation";"Select Medical - Implementation";"Buckets Master";"open";"";
6455;"Payer AFL Details";"Implementation";"Select Medical - Implementation";"Payer AFL Details";"open";"";
6454;"Payer TFL Details";"Implementation";"Select Medical - Implementation";"Payer TFL Details";"open";"";
6453;"Action Codes";"Implementation";"Select Medical - Implementation";"Action Codes";"open";"";
6452;"Status Codes";"Implementation";"Select Medical - Implementation";"Status Codes";"open";"";
6451;"AR Groupings (Specialty/Payers wise / FC's / Service Lines) ";"Implementation";"Select Medical - Implementation";"AR Groupings (Specialty/Payers wise / FC's / Service Lines)";"open";"";
6450;"Templates to be shared with Select Process Owners";"Implementation";"Select Medical - Implementation";"Templates to be shared with Select Process Owners";"open";"";
6449;"Implementation consultant to validate the template to ensure masters are as expected";"Implementation";"Select Medical - Implementation";"Implementation consultant to validate the template to ensure masters
are as expected";"open";"";
6448;"Select Medical process owners to share the filled Masters with Implementation Team";"Implementation";"Select Medical - Implementation";"Select Medical process owners to share the filled Masters with
Implementation Team";"open";"";
6447;"Select Medical process owners to fill the data in the given template";"Implementation";"Select Medical - Implementation";"Select Medical process owners to fill the data in the given template";"open";"";
6446;"Explain the template(s) to Select Medical process owners ";"Implementation";"Select Medical - Implementation";"Explain the template(s) to Select Medical process owners";"open";"";
6445;"Share the master template(s) with Select Team process owners ";"Implementation";"Select Medical - Implementation";"Share the master template(s) with Select Team process owners";"open";"";
6444;"Masters Data Collections Template Share";"Implementation";"Select Medical - Implementation";"Masters Data Collections Template Share";"open";"";
6443;"Sign-off on the defined Optimix to-be tasking process ";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6442;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6441;"Define Clinics In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define Clinics In-Coming task buckets responsibility";"open";"";
6440;"Define Clinics In-Coming tasks and buckets based on the agreed standard process between PTA process ";"Implementation";"Select Medical - Implementation";"Define Clinics In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6439;"Design Clinics out-going tasks and buckets based on the agreed standard process between PTA process ";"Implementation";"Select Medical - Implementation";"Design Clinics out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6438;"Detailed explanation to the Implementation process consultant on the agreed standard Operations proc";"Implementation";"Select Medical - Implementation";"Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners";"open";"";
6437;"Process Fitment - Clinics Tasking Process Design";"Implementation";"Select Medical - Implementation";"Process Fitment - Clinics Tasking Process Design";"open";"";
6436;"Incase of discrepancy revert back to the Select and close the gap";"Implementation";"Select Medical - Implementation";"Incase of discrepancy revert back to the Select and close the gap";"open";"";
6435;"Validate configuration | access & required s/w";"Implementation";"Select Medical - Implementation";"Validate configuration | access & required s/w";"open";"";
6434;"Provide required IT Infrastructure | Access to Optimix team";"Implementation";"Select Medical - Implementation";"Provide required IT Infrastructure | Access to Optimix team";"open";"";
6433;"Explain the infrastructure requirement to Select IT ";"Implementation";"Select Medical - Implementation";"Explain the infrastructure requirement to Select IT";"open";"";
6432;"Prepare the IT infrastructure requirement specification document and share the same with Select IT";"Implementation";"Select Medical - Implementation";"Prepare the IT infrastructure requirement specification document and
share the same with Select IT";"open";"";
6431;"Understand the type/size of business and define the infrastructure requirement ";"Implementation";"Select Medical - Implementation";"Understand the type/size of business and define the infrastructure
requirement";"open";"";
6430;"Identify IT point of contact to coordinate with IKS technical implementation team";"Implementation";"Select Medical - Implementation";"Identify IT point of contact to coordinate with IKS technical
implementation team";"open";"";
6429;"Infrastructure Requirement";"Implementation";"Select Medical - Implementation";"Infrastructure Requirement";"open";"";
6424;"Travel ticket and the required documentations are prepared and shared with the Optimix Implementatio";"Implementation";"Select Medical - Implementation";"Travel ticket and the required documentations are prepared and shared
with the Optimix Implementation team";"open";"";
6423;"Booking of Flight tickets for travel of Implementation team";"Implementation";"Select Medical - Implementation";"Booking of Flight tickets for travel of Implementation team";"open";"";
6422;"Select medical provides the necessary approval on the travel plan";"Implementation";"Select Medical - Implementation";"Select medical provides the necessary approval on the travel plan";"open";"";
6421;"Share the travel plan Select for approval on the Implementation resource travel";"Implementation";"Select Medical - Implementation";"Share the travel plan Select for approval on the Implementation
resource travel";"open";"";
6420;"Prepare the travel plan for IKS implementation resources to travel onsite to accomplish key Implemen";"Implementation";"Select Medical - Implementation";"Prepare the travel plan for IKS implementation resources to travel
onsite to accomplish key Implementation activities";"open";"";
6419;"Implementation Team Travel Plan";"Implementation";"Select Medical - Implementation";"Implementation Team Travel Plan";"open";"";
6418;"SOW Sign-Off by Select Medical";"Implementation";"Select Medical - Implementation";"SOW Sign-Off by Select Medical";"open";"";
6417;"Finalized SOW copy sent to the relevant stake holders for Sign-off";"Implementation";"Select Medical - Implementation";"Finalized SOW copy sent to the relevant stake holders for Sign-off";"open";"";
6416;"Select confirms on the SOW to IKS";"Implementation";"Select Medical - Implementation";"Select confirms on the SOW to IKS";"open";"";
6415;"Make amendments / Changes | if any | and revert back for confirmation from Select";"Implementation";"Select Medical - Implementation";"Make amendments / Changes | if any | and revert back for confirmation
from Select";"open";"";
6414;"Select Medical reviews the SOW and send back to IKS";"Implementation";"Select Medical - Implementation";"Select Medical reviews the SOW and send back to IKS";"open";"";
6413;"Prepare SOW and shares the same with Select Medical";"Implementation";"Select Medical - Implementation";"Prepare SOW and shares the same with Select Medical";"open";"";
6411;"Detailed explanation to the Implementation process consultant on the agreed standard Operations proc";"Implementation";"Select Medical - Implementation";"Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners";"open";"";
6410;"Design Clinics out-going tasks and buckets based on the agreed standard process between PTA process";"Implementation";"Select Medical - Implementation";"Design Clinics out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6409;"Define Other entities team In-Coming tasks and buckets based on the agreed standard process between";"Implementation";"Select Medical - Implementation";" Define Other entities team In-Coming tasks and buckets based on the
agreed standard process between PTA process owners and Select Process
Owners
";"open";"";
6407;"Statement of Work";"Implementation";"Select Medical - Implementation";"Statement ofWork";"open";"";
6406;"Share the project plan with all the stake holders post confirmation from Select";"Implementation";"Select Medical - Implementation";" Share the project plan with all the stake holders post confirmation
from Select
";"open";"";
6404;"Approval on the project plan";"Implementation";"Select Medical - Implementation";"Approval on the project plan";"open";"";
6403;"Make the changes | if any | in the project plan and share the same with Select";"Implementation";"Select Medical - Implementation";"Make the changes | if any | in the project plan and share the same with
Select";"open";"";
6402;"Discuss for any changes on the dates and the resources to be point of contact for each process from";"Implementation";"Select Medical - Implementation";"Discuss for any changes on the dates and the resources to be point of
contact for each process from Select and resource to be the project
manager from Select";"open";"";
6401;"Share and explain the project plan in the scheduled call";"Implementation";"Select Medical - Implementation";"Share and explain the project plan in the scheduled call";"open";"";
6400;"Check for Select leadership availability for a scheduled call";"Implementation";"Select Medical - Implementation";"Check for Select leadership availability for a scheduled call";"open";"";
6399;"Kick-Off call with Select Medical";"Implementation";"Select Medical - Implementation";"Kick-Off call with Select Medical";"open";"";
6370;"Sign-off on the defined Optimix to-be tasking process";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6369;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6368;"Define rejection team In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define rejection team In-Coming task buckets responsibility";"open";"";
6367;"Define rejection team In-Coming tasks and buckets based on the agreed standard process between PTA p";"Implementation";"Select Medical - Implementation";"Define rejection team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6366;"Design rejection team out-going tasks and buckets based on the agreed standard process between PTA p";"Implementation";"Select Medical - Implementation";"Design rejection team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6365;"Sign-off on the Optimix to-be process document";"Implementation";"Select Medical - Implementation";"Sign-off on the Optimix to-be process document";"open";"";
6364;"Document the Optimix to-be Rejections workflow management process based on the agreed standard proce";"Implementation";"Select Medical - Implementation";"Document the Optimix to-be Rejections workflow management process
based on the agreed standard process between PTA process owners and
Select Process Owners";"open";"";
6360;"Sign-off on the defined Optimix to-be tasking process";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6359;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6358;"Define Other entities team In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define Other entities team In-Coming task buckets responsibility";"open";"";
6354;"Process Fitment - Other Entity Tasking Process Design";"Implementation";"Select Medical - Implementation";"Process Fitment - Other Entity Tasking Process Design";"open";"";
6353;"Sign-off on the defined Optimix to-be tasking process";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6352;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6351;"Define PP team In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define PP team In-Coming task buckets responsibility";"open";"";
6350;"Define PP team In-Coming tasks and buckets based on the agreed standard process between PTA process";"Implementation";"Select Medical - Implementation";"Define PP team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6349;"Design PP team out-going tasks and buckets based on the agreed standard process between PTA process";"Implementation";"Select Medical - Implementation";"Design PP team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6348;"Detailed explanation to the Implementation process consultant on the agreed standard Operations proc";"Implementation";"Select Medical - Implementation";"Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners";"open";"";
6347;"Process Fitment - PP Tasking Process Design";"Implementation";"Select Medical - Implementation";"Process Fitment - PP Tasking Process Design";"open";"";
6346;"Sign-Off on the rules and buckets";"Implementation";"Select Medical - Implementation";"Sign-Off on the rules and buckets";"open";"";
6345;"Document the rules & buckets";"Implementation";"Select Medical - Implementation";"Document the rules & buckets";"open";"";
6344;"Design PAR/RA Rules & Buckets";"Implementation";"Select Medical - Implementation";"Design PAR/RA Rules & Buckets";"open";"";
6343;"CSR AS-IS strategy discussion";"Implementation";"Select Medical - Implementation";"CSR AS-IS strategy discussion";"open";"";
6342;"RA AS-IS Strategy discussion";"Implementation";"Select Medical - Implementation";"RA AS-IS Strategy discussion";"open";"";
6341;"PAR AS-IS Strategy discussion";"Implementation";"Select Medical - Implementation";"PAR AS-IS Strategy discussion";"open";"";
6340;"Process Fitment - PAR / CSR Operations Strategy and Tasking workflow Design";"Implementation";"Select Medical - Implementation";"Process Fitment - PAR / CSR Operations Strategy and Tasking workflow
Design";"open";"";
6339;"Sign-off on the defined Optimix to-be tasking process";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6338;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6337;"Define rejection team In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define rejection team In-Coming task buckets responsibility";"open";"";
6336;"Define rejection team In-Coming tasks and buckets based on the agreed standard process between PTA p";"Implementation";"Select Medical - Implementation";"Define rejection team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6335;"Design rejection team out-going tasks and buckets based on the agreed standard process between PTA p";"Implementation";"Select Medical - Implementation";"Design rejection team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners";"open";"";
6334;"Sign-off on the Optimix to-be process document";"Implementation";"Select Medical - Implementation";"Sign-off on the Optimix to-be process document";"open";"";
6333;"Document the Optimix to-be Rejections workflow management process based on the agreed standard proce";"Implementation";"Select Medical - Implementation";"Document the Optimix to-be Rejections workflow management process
based on the agreed standard process between PTA process owners and
Select Process Owners";"open";"";
6331;"Perform Gap Analysis to identify any Gaps between Optimix process and the designed standard Strategy";"Implementation";"Select Medical - Implementation";"Perform Gap Analysis to identify any Gaps between Optimix process and
the designed standard Strategy";"open";"";
6330;"Design the Operations team Hierarchy based on the agreed standard process between PTA process owners";"Implementation";"Select Medical - Implementation";"Design the Operations team Hierarchy based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6329;"Design rejections workable inventory rules logics and buckets based on the agreed standard process b";"Implementation";"Select Medical - Implementation";"Design rejections workable inventory rules logics and buckets based on
the agreed standard process between PTA process owners and Select
Process Owners";"open";"";
6328;"Design Exceptional logics based on the agreed standard process between PTA process owners and Select";"Implementation";"Select Medical - Implementation";"Design Exceptional logics based on the agreed standard process between
PTA process owners and Select Process Owners";"open";"";
6327;"Design Exclusion rules logics and buckets based on the agreed standard process between PTA process";"Implementation";"Select Medical - Implementation";"Design Exclusion rules logics and buckets based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6326;"Design Rejection Groupings based on the agreed standard process between PTA process owners and Selec";"Implementation";"Select Medical - Implementation";"Design Rejection Groupings based on the agreed standard process
between PTA process owners and Select Process Owners";"open";"";
6325;"Detailed explanation to the Implementation process consultant on the agreed standard Operations proc";"Implementation";"Select Medical - Implementation";"Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners";"open";"";
6324;"Process Fitment - Rejections Operation Strategy and Tasking Process Design";"Implementation";"Select Medical - Implementation";"Process Fitment - Rejections Operation Strategy and Tasking Process
Design";"open";"";
6323;"Sign-off on the defined Optimix to-be tasking process";"Implementation";"Select Medical - Implementation";"Sign-off on the defined Optimix to-be tasking process";"open";"";
6322;"Design the standard tasking buckets and document the tasking work flow process";"Implementation";"Select Medical - Implementation";"Design the standard tasking buckets and document the tasking work flow
process";"open";"";
6321;"Define AR In-Coming task buckets responsibility";"Implementation";"Select Medical - Implementation";"Define AR In-Coming task buckets responsibility";"open";"";
6320;"Define AR In-Coming tasks and buckets based on the agreed standard process between PTA process owner";"Implementation";"Select Medical - Implementation";"Define AR In-Coming tasks and buckets based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6319;"Design AR Out-Going tasks and buckets based on the agreed standard process between PTA process owner";"Implementation";"Select Medical - Implementation";"Design AR Out-Going tasks and buckets based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6318;"Sign-off on the Optimix to-be process document";"Implementation";"Select Medical - Implementation";"Sign-off on the Optimix to-be process document";"open";"";
6317;"Document the Optimix to-be AR & Denial Operations workflow management process based on the agreed s";"Implementation";"Select Medical - Implementation";"Document the Optimix to-be AR & Denial Operations workflow management
process based on the agreed standard process between PTA process
owners and Select Process Owners";"open";"";
6316;"Perform Gap Analysis to identify any Gaps between Optimix process and the designed standard Strategy";"Implementation";"Select Medical - Implementation";"Perform Gap Analysis to identify any Gaps between Optimix process and
the designed standard Strategy";"open";"";
6315;"Design the Operations team Hierarchy based on the agreed standard process between PTA process owners";"Implementation";"Select Medical - Implementation";"Design the Operations team Hierarchy based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6314;"Design AR and Denial workable inventory rules logics and buckets based on the agreed standard proces";"Implementation";"Select Medical - Implementation";"Design AR and Denial workable inventory rules logics and buckets based
on the agreed standard process between PTA process owners and Select
Process Owners";"open";"";
6313;"Design Exceptional logics based on the agreed standard process between PTA process owners and Select";"Implementation";"Select Medical - Implementation";"Design Exceptional logics based on the agreed standard process between
PTA process owners and Select Process Owners";"open";"";
6312;"Design Exclusion rules logics and buckets based on the agreed standard process between PTA process";"Implementation";"Select Medical - Implementation";"Design Exclusion rules logics and buckets based on the agreed standard
process between PTA process owners and Select Process Owners";"open";"";
6311;"Design External Groupings (Payers/FC/Location/Denials/Clinic) based on the agreed standard process b";"Implementation";"Select Medical - Implementation";"Design External Groupings (Payers/FC/Location/Denials/Clinic) based on
the agreed standard process between PTA process owners and Select
Process Owners";"open";"";
6310;"Detailed explanation to the Implementation process consultant on the agreed standard Operations proc";"Implementation";"Select Medical - Implementation";"Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners";"open";"";
6309;"Process Fitment - AR/Denial Operation Strategy and Tasking Process Design";"Implementation";"Select Medical - Implementation";"Process Fitment - AR/Denial Operation Strategy and Tasking Process
Design";"open";"";
6308;"Sign-off on the agreed process flow";"Implementation";"Select Medical - Implementation";"Sign-off on the agreed process flow";"open";"";
6307;"Document the finalized Clinic tasking workflow process across PTA and select Medical Operations";"Implementation";"Select Medical - Implementation";"Document the finalized Clinic tasking workflow process across PTA and
select Medical Operations";"open";"";
6306;"Standardization of the Clinic tasking workflow process between PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Standardization of the Clinic tasking workflow process between PTA and
Select Medical";"open";"";
6305;"Discuss the Current Clinic tasking workflow process between PTA and Select Medical Process owners";"Implementation";"Select Medical - Implementation";"Discuss the Current Clinic tasking workflow process between PTA and
Select Medical Process owners";"open";"";
6304;"Sign-off on the agreed process flow";"Implementation";"Select Medical - Implementation";"Sign-off on the agreed process flow";"open";"";
6302;"Document the finalized Other Entity tasking workflow process across PTA and select Medical Operation";"Implementation";"Select Medical - Implementation";"Document the finalized Other Entity tasking workflow process across
PTA and select Medical Operations";"open";"";
6301;"Standardization of the Other Entity tasking workflow process between PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Standardization of the Other Entity tasking workflow process between
PTA and Select Medical";"open";"";
6300;"Discuss the Current Other Entity tasking workflow process between PTA and Select Medical Process own";"Implementation";"Select Medical - Implementation";"Discuss the Current Other Entity tasking workflow process between PTA
and Select Medical Process owners";"open";"";
6299;"Sign-off on the agreed process flow";"Implementation";"Select Medical - Implementation";"Sign-off on the agreed process flow";"open";"";
6298;"Document the finalized rejection management workflow process across PTA and select Medical Operation";"Implementation";"Select Medical - Implementation";"Document the finalized rejection management workflow process across
PTA and select Medical Operations";"open";"";
6297;"Standardization of the Rejection Management Workflow process between PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Standardization of the Rejection Management Workflow process between
PTA and Select Medical";"open";"";
6296;"Discuss the Current Rejections handling process workflow between PTA and Select Medical Process owne";"Implementation";"Select Medical - Implementation";"Discuss the Current Rejections handling process workflow between PTA
and Select Medical Process owners";"open";"";
6295;"Sign-off on the agreed process flow";"Implementation";"Select Medical - Implementation";"Sign-off on the agreed process flow";"open";"";
6294;"Document the finalized rejection management workflow process across PTA and select Medical Operation";"Implementation";"Select Medical - Implementation";"Document the finalized rejection management workflow process across
PTA and select Medical Operations";"open";"";
6293;"Standardization of the Rejection Management Workflow process between PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Standardization of the Rejection Management Workflow process between
PTA and Select Medical";"open";"";
6292;"Discuss the Current Rejections handling process workflow between PTA and Select Medical Process owne";"Implementation";"Select Medical - Implementation";"Discuss the Current Rejections handling process workflow between PTA
and Select Medical Process owners";"open";"";
6291;"Sign-off on the agreed process flow";"Implementation";"Select Medical - Implementation";"Sign-off on the agreed process flow";"open";"";
6290;"Document the finalized standard workflow process across PTA and select Medical Operations";"Implementation";"Select Medical - Implementation";"Document the finalized standard workflow process across PTA and select
Medical Operations";"open";"";
6289;"Standardization of the AR workflow process between PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Standardization of the AR workflow process between PTA and Select
Medical";"open";"";
6288;"Discuss on the Current AR Operations workflow process of PTA and Select Medical";"Implementation";"Select Medical - Implementation";"Discuss on the Current AR Operations workflow process of PTA and
Select Medical";"open";"";
6287;"Operations Process Fitment - PTA/Select Workflow Calibration";"Implementation";"Select Medical - Implementation";"Operations Process Fitment - PTA/Select Workflow Calibration";"open";"";
6286;"Final Sign-off on the understanding of the scope for Optimix Implementation";"Implementation";"Select Medical - Implementation";"Final Sign-off on the understanding of the scope for Optimix
Implementation";"open";"";
6285;"Optimix Implementation team reviews and understand the scope document and come up with questions if";"Implementation";"Select Medical - Implementation";"Optimix Implementation team reviews and understand the scope document
and come up with questions if any for clarification";"open";"";
6284;"Revert back the filled in scope document to Optimix Implementation team for the team review and scop";"Implementation";"Select Medical - Implementation";"Revert back the filled in scope document to Optimix Implementation
team for the team review and scope understanding";"open";"";
6283;"Fill in the Scope document with the relevant information";"Implementation";"Select Medical - Implementation";"Fill in the Scope document with the relevant information";"open";"";
6282;"Share the Scope document template with the Select Project Manager";"Implementation";"Select Medical - Implementation";"Share the Scope document template with the Select Project Manager";"open";"";
6281;"Initiate the Optimix Scope discussion with the respective Select Project Manager";"Implementation";"Select Medical - Implementation";"Initiate the Optimix Scope discussion with the respective Select
Project Manager";"open";"";
6280;"Address CBO teams and introduce the implementation team";"Implementation";"Select Medical - Implementation";"Address CBO teams and introduce the implementation team";"open";"";
6279;"Scope";"Implementation";"Select Medical - Implementation";"Scope";"open";"";
6278;"Validate the monitoring process";"Implementation";"Select Medical - Implementation";"Validate the monitoring process";"open";"";
6277;"Design the process flow which will call out the time of file placement | folder of file placement | sc";"Implementation";"Select Medical - Implementation";"Design the process flow which will call out the time of file
placement | folder of file placement | scheduled time of the script
execution and monitoring phase";"open";"";
6276;"Test the scripts /data feed files in the UAT server";"Implementation";"Select Medical - Implementation";"Test the scripts /data feed files in the UAT server";"open";"";
6275;"Deploy the scripts/data feed files in the UAT server";"Implementation";"Select Medical - Implementation";"Deploy the scripts/data feed files in the UAT server";"open";"";
6274;"Develop scripts /data feed files as specified by IKS Implementation tech team";"Implementation";"Select Medical - Implementation";"Develop scripts /data feed files as specified by IKS Implementation
tech team";"open";"";
6273;"Send the required data set list to the client IT team and get the required data set";"Implementation";"Select Medical - Implementation";"Send the required data set list to the client IT team and get the
required data set";"open";"";
6256;"Data Extraction from RT";"Implementation";"Select Medical - Implementation";"Data Extraction from RT";"open";"";
6255;"Access from the Clinic machines and check if the user is able to access the application from Clinics";"Implementation";"Select Medical - Implementation";"Access from the Clinic machines and check if the user is able to
access the application from Clinics";"open";"";
6254;"Access from the node machines and check if the user is able to access the application from CBO's";"Implementation";"Select Medical - Implementation";"Access from the node machines and check if the user is able to access
the application from CBO's";"open";"";
6253;"Validated that the basic Configurations/Entities are available as expected";"Implementation";"Select Medical - Implementation";"Validated that the basic Configurations/Entities are available as
expected";"open";"";
6252;"Deploy Optimix Application in the Production environment";"Implementation";"Select Medical - Implementation";"Deploy Optimix Application in the Production environment";"open";"";
6251;"Deploy Optimix Application in the UAT environment";"Implementation";"Select Medical - Implementation";"Deploy Optimix Application in the UAT environment";"open";"";
6250;"Optimix Configuration";"Implementation";"Select Medical - Implementation";"Optimix Configuration";"open";"";

## Sheet2
id | name | activity type | project | description | status | result
6672 | Sign-off and send the approval for "Optimix Go Live" to Optimix Implementation team | Implementation | Select Medical - Implementation | Sign-off and send the approval for "Optimix Go Live" to Optimix
Implementation team" | open
6671 | Discuss with all the stake holders to get a joint confirmation readiness to Go Live in the Go No-go | Implementation | Select Medical - Implementation | Discuss with all the stake holders to get a joint confirmation
readiness to Go Live in the Go No-go call. Incase of a No-go need to
decide on the revised Go Live date and inform all the executive team
with valid reasons" | open
6670 | Send the Go No Go call invitation to all the stake holders 5 days in advance | Implementation | Select Medical - Implementation | Send the Go No Go call invitation to all the stake holders 5 days in
advance" | open
6669 | Work on Patches if any show stopper | Implementation | Select Medical - Implementation | Work on Patches if any show stopper | open
6668 | List down the findings if any in the testing and share the same with Optimix Implementation team | Implementation | Select Medical - Implementation | List down the findings if any in the testing and share the same with
Optimix Implementation team" | open
6667 | Select Medical Optimix users team start using IKS remote support service | Implementation | Select Medical - Implementation | Select Medical Optimix users team start using IKS remote support
service" | open
6666 | Sign-Off email in agreement on completion of IKS Optimix Implementation services and readiness to us | Implementation | Select Medical - Implementation | Sign-Off email in agreement on completion of IKS Optimix
Implementation services and readiness to use IKS remote support
services" | open
6665 | Discussion the transition from implementation services to remote support services. Elaborate the Sup | Implementation | Select Medical - Implementation | Discussion the transition from implementation services to remote
support services. Elaborate the Support contact information
escalation metrics
escalation metrics to Select Process Owners" | open
6664 | Plan and setup a transition call between Select Process Owners
Ops
6663 | Support team sign-off on the understanding of Knowledge transfer and documents shared by Optimix imp | Implementation | Select Medical - Implementation | Support team sign-off on the understanding of Knowledge transfer and
documents shared by Optimix implementation team." | open
6662 | Fill and share the documents related to transition from implementation phase to remote support phase | Implementation | Select Medical - Implementation | Fill and share the documents related to transition from implementation
phase to remote support phase during the knowledge sharing session." | open
6661 | Knowledge transfer on Select medical process
set-up in Optimix
issues and additional information to be shared." | open
6660 | Plan and setup the knowledge transfer call between IKS remote support manager
manager
team." | open
6659 | Move To Remote Support | Implementation | Select Medical - Implementation | Move To Remote Support | open
6658 | Go Live | Implementation | Select Medical - Implementation | Go Live | open
6657 | Roll out the email for completion of production environment setup | Implementation | Select Medical - Implementation | Roll out the email for completion of production environment setup | open
6656 | sign-off on the testing and completion of patches | Implementation | Select Medical - Implementation | sign-off on the testing and completion of patches | open
6655 | rectifying/testing patches if any Show Stopper | Implementation | Select Medical - Implementation | rectifying/testing patches if any Show Stopper | open
6654 | Select Operations users working and testing the regular flow in Live environment with minimal data | Implementation | Select Medical - Implementation | Select Operations users working and testing the regular flow in Live
environment with minimal data" | open
6653 | Identify the Inventory for testing the live production site | Implementation | Select Medical - Implementation | Identify the Inventory for testing the live production site | open
6652 | Prepare Live working scenarios based on current days Operation | Implementation | Select Medical - Implementation | Prepare Live working scenarios based on current days Operation | open
6651 | Prepare the checklist for activities to be performed during testing | Implementation | Select Medical - Implementation | Prepare the checklist for activities to be performed during testing | open
6650 | Go Live Prep - Production Environment Testing | Implementation | Select Medical - Implementation | Go Live Prep - Production Environment Testing | open
6649 | Smoke testing Patches if any Show Stopper | Implementation | Select Medical - Implementation | Smoke testing Patches if any Show Stopper | open
6648 | Smoke Testing | Implementation | Select Medical - Implementation | Smoke Testing | open
6647 | IIS Setting Change for AD user | Implementation | Select Medical - Implementation | IIS Setting Change for AD user | open
6646 | Execute Rule Engine | Implementation | Select Medical - Implementation | Execute Rule Engine | open
6645 | Reset Bucket and User for AR Encounters | Implementation | Select Medical - Implementation | Reset Bucket and User for AR Encounters | open
6644 | Additional Data Import if any | Implementation | Select Medical - Implementation | Additional Data Import if any | open
6643 | Configure/Verify the Backup Schedule | Implementation | Select Medical - Implementation | Configure/Verify the Backup Schedule | open
6642 | Update the Web Config File in Production | Implementation | Select Medical - Implementation | Update the Web Config File in Production | open
6641 | Deploy the Code to Production Except Web Config | Implementation | Select Medical - Implementation | Deploy the Code to Production Except Web Config | open
6640 | All Grouping configuration From UAT to PROD | Implementation | Select Medical - Implementation | All Grouping configuration From UAT to PROD | open
6639 | Move Search Related Data from UAT to PROD | Implementation | Select Medical - Implementation | Move Search Related Data from UAT to PROD | open
6638 | Move bucket Mapping Details from UAT to PROD | Implementation | Select Medical - Implementation | Move bucket Mapping Details from UAT to PROD | open
6637 | Move Users Bucket From UAT to PROD | Implementation | Select Medical - Implementation | Move Users Bucket From UAT to PROD | open
6636 | Move Users Data From UAT to PROD | Implementation | Select Medical - Implementation | Move Users Data From UAT to PROD | open
6635 | Move Rule Engine Configuration From UAT to PROD | Implementation | Select Medical - Implementation | Move Rule Engine Configuration From UAT to PROD | open
6634 | Move Bucket Data from UAT to PROD | Implementation | Select Medical - Implementation | Move Bucket Data from UAT to PROD | open
6633 | Execute Script to Create Indexes | Implementation | Select Medical - Implementation | Execute Script to Create Indexes | open
6632 | Execute Alter Script for Data type Changes | Implementation | Select Medical - Implementation | Execute Alter Script for Data type Changes | open
6631 | Execute Alter Script for Additional Columns | Implementation | Select Medical - Implementation | Execute Alter Script for Additional Columns | open
6630 | Execute Create table Scripts | Implementation | Select Medical - Implementation | Execute Create table Scripts | open
6629 | Take Production Code Backup | Implementation | Select Medical - Implementation | Take Production Code Backup | open
6628 | Take Production DB Backup. | Implementation | Select Medical - Implementation | Take Production DB Backup. | open
6627 | Create Separate Folder for Upgrade activities | Implementation | Select Medical - Implementation | Create Separate Folder for Upgrade activities | open
6626 | Bring down the live site in IIS | Implementation | Select Medical - Implementation | Bring down the live site in IIS | open
6625 | Prepare the Checklist with the list activities Tobe performed for deployment | Implementation | Select Medical - Implementation | Prepare the Checklist with the list activities Tobe performed for
deployment" | open
6624 | Go Live Prep - DB Migration and Masters Migration | Implementation | Select Medical - Implementation | Go Live Prep - DB Migration and Masters Migration | open
6623 | Deploy the migration in production | Implementation | Select Medical - Implementation | Deploy the migration in production | open
6622 | Sign-Off on the data migration post completion of validation | Implementation | Select Medical - Implementation | Sign-Off on the data migration post completion of validation | open
6621 | Validate the migrated data in the UAT server post deployment and execution of the migration scripts | Implementation | Select Medical - Implementation | Validate the migrated data in the UAT server post deployment and
execution of the migration scripts" | open
6620 | Testing of the migration scripts in the UAT Server | Implementation | Select Medical - Implementation | Testing of the migration scripts in the UAT Server | open
6619 | Deploy the migration scripts in the UAT server for testing | Implementation | Select Medical - Implementation | Deploy the migration scripts in the UAT server for testing | open
6618 | Build the migration scripts based on the identified legacy data | Implementation | Select Medical - Implementation | Build the migration scripts based on the identified legacy data | open
6617 | Analyze and identify the legacy data that needs to be migrated to Optimix | Implementation | Select Medical - Implementation | Analyze and identify the legacy data that needs to be migrated to
Optimix" | open
6616 | Go Live Prep - Legacy Data Migration to Optimix | Implementation | Select Medical - Implementation | Go Live Prep - Legacy Data Migration to Optimix | open
6614 | DARE Summary Report validation | Implementation | Select Medical - Implementation | DARE Summary Report validation | open
6613 | Tasking Detailed Report validation | Implementation | Select Medical - Implementation | Tasking Detailed Report validation | open
6612 | Tasking Detailed Report validation | Implementation | Select Medical - Implementation | Tasking Detailed Report validation | open
6611 | Tasking Summary Report validation | Implementation | Select Medical - Implementation | Tasking Summary Report validation | open
6610 | Production Report validation | Implementation | Select Medical - Implementation | Production Report validation | open
6609 | Activity Report validation | Implementation | Select Medical - Implementation | Activity Report validation | open
6608 | Other entities workorder activities - Tasking to other entities | Implementation | Select Medical - Implementation | Other entities workorder activities - Tasking to other entities | open
6607 | Other entities workorder activities - Task completion | Implementation | Select Medical - Implementation | Other entities workorder activities - Task completion | open
6606 | Other entities tasks allocation | Implementation | Select Medical - Implementation | Other entities tasks allocation | open
6605 | Other entities workorder activities - Tasking to other entities | Implementation | Select Medical - Implementation | Other entities workorder activities - Tasking to other entities | open
6604 | Other entities workorder activities - Task completion | Implementation | Select Medical - Implementation | Other entities workorder activities - Task completion | open
6603 | Other entities tasks allocation | Implementation | Select Medical - Implementation | Other entities tasks allocation | open
6602 | PP - Incoming tasks work flow | Implementation | Select Medical - Implementation | PP - Incoming tasks work flow | open
6601 | PP incoming tasks allocation | Implementation | Select Medical - Implementation | PP incoming tasks allocation | open
6600 | PP Work Order activities - Tasks over task and return task flow | Implementation | Select Medical - Implementation | PP Work Order activities - Tasks over task and return task flow | open
6599 | PP Work Order activities - Tasks Completion | Implementation | Select Medical - Implementation | PP Work Order activities - Tasks Completion | open
6598 | PP - Rejections Tasks Allocation | Implementation | Select Medical - Implementation | PP - Rejections Tasks Allocation | open
6597 | Billing - Incoming tasks work flow | Implementation | Select Medical - Implementation | Billing - Incoming tasks work flow | open
6596 | Billing incoming tasks allocation | Implementation | Select Medical - Implementation | Billing incoming tasks allocation | open
6595 | Billing Work Order activities - Tasks over task and return task flow | Implementation | Select Medical - Implementation | Billing Work Order activities - Tasks over task and return task flow | open
6594 | Billing Work Order activities - Tasks Completion | Implementation | Select Medical - Implementation | Billing Work Order activities - Tasks Completion | open
6593 | Billing - Rejections Tasks Allocation | Implementation | Select Medical - Implementation | Billing - Rejections Tasks Allocation | open
6592 | Denial Incoming tasks from Other entities | Implementation | Select Medical - Implementation | Denial Incoming tasks from Other entities | open
6591 | Denial incoming tasks work allocation | Implementation | Select Medical - Implementation | Denial incoming tasks work allocation | open
6590 | Denial work order activities - Task to other entities | Implementation | Select Medical - Implementation | Denial work order activities - Task to other entities | open
6589 | Denial work order activities - Encounter completion | Implementation | Select Medical - Implementation | Denial work order activities - Encounter completion | open
6588 | Denial Work allocation | Implementation | Select Medical - Implementation | Denial Work allocation | open
6587 | AR Incoming tasks working from Other entities | Implementation | Select Medical - Implementation | AR Incoming tasks working from Other entities | open
6586 | AR incoming tasks work allocation | Implementation | Select Medical - Implementation | AR incoming tasks work allocation | open
6585 | AR work order activities - Tasking to other entities and return task flow | Implementation | Select Medical - Implementation | AR work order activities - Tasking to other entities and return task
flow" | open
6584 | AR work order activities - Encounter completion | Implementation | Select Medical - Implementation | AR work order activities - Encounter completion | open
6583 | AR Work allocation | Implementation | Select Medical - Implementation | AR Work allocation | open
6582 | User Acceptance Test - Activities | Implementation | Select Medical - Implementation | User Acceptance Test - Activities | open
6581 | Schedule the rejection import scripts in the UAT environment | Implementation | Select Medical - Implementation | Schedule the rejection import scripts in the UAT environment | open
6580 | Import of AR data from RT in UAT environment and scheduling the scripts for bringing in the delta da | Implementation | Select Medical - Implementation | Import of AR data from RT in UAT environment and scheduling the
scripts for bringing in the delta data." | open
6579 | Rejection file import scripts to be deployed in the UAT process | Implementation | Select Medical - Implementation | Rejection file import scripts to be deployed in the UAT process | open
6578 | Data Import scripts deployment in the UAT environment | Implementation | Select Medical - Implementation | Data Import scripts deployment in the UAT environment | open
6577 | UAT environment preparation and Optimix Deployment | Implementation | Select Medical - Implementation | UAT environment preparation and Optimix Deployment | open
6576 | User Acceptance Test - Environment Setup and Data Import | Implementation | Select Medical - Implementation | User Acceptance Test - Environment Setup and Data Import | open
6575 | Send an email confirmation to Optimix implementation team on the readiness for the UAT phase | Implementation | Select Medical - Implementation | Send an email confirmation to Optimix implementation team on the
readiness for the UAT phase" | open
6574 | Send the communication to all the select Optimix users on the start date of UAT
date of UAT
6573 | Fix the resources and the inventory to work during the UAT phase | Implementation | Select Medical - Implementation | Fix the resources and the inventory to work during the UAT phase | open
6572 | Discuss the plan with Select Process owners and explain the expectation the inventory and the resour | Implementation | Select Medical - Implementation | Discuss the plan with Select Process owners and explain the
expectation the inventory and the resources to be available for UAT" | open
6571 | Prepare and share the standard UAT plan to select process owners | Implementation | Select Medical - Implementation | Prepare and share the standard UAT plan to select process owners | open
6570 | User Acceptance Test - Planning | Implementation | Select Medical - Implementation | User Acceptance Test - Planning | open
6569 | Task responsibility detailed report to identify their respective clinics responsibility inventory an | Implementation | Select Medical - Implementation | Task responsibility detailed report to identify their respective
clinics responsibility inventory and bifurcation of the tasks" | open
6568 | Task Summary report extraction to identify their respective clinics pending/in progress tasks | Implementation | Select Medical - Implementation | Task Summary report extraction to identify their respective clinics
pending/in progress tasks" | open
6567 | Return task flow set-up in Optimix | Implementation | Select Medical - Implementation | Return task flow set-up in Optimix | open
6566 | Tasking work order screen features | Implementation | Select Medical - Implementation | Tasking work order screen features | open
6565 | Working on a task in Optimix | Implementation | Select Medical - Implementation | Working on a task in Optimix | open
6564 | Tasking workflow set-up in Optimix | Implementation | Select Medical - Implementation | Tasking workflow set-up in Optimix | open
6563 | Training to Clinics/RCM's | Implementation | Select Medical - Implementation | Training to Clinics/RCM's | open
6562 | Looking in to individual hourly production | Implementation | Select Medical - Implementation | Looking in to individual hourly production | open
6561 | Working on rejected tasks from a supervisor | Implementation | Select Medical - Implementation | Working on rejected tasks from a supervisor | open
6560 | Working on incoming tasks inventory | Implementation | Select Medical - Implementation | Working on incoming tasks inventory | open
6559 | Tasking from an encounter
6558 | Completing an encounter/ task | Implementation | Select Medical - Implementation | Completing an encounter/ task | open
6557 | Forwarding an encounter/ task | Implementation | Select Medical - Implementation | Forwarding an encounter/ task | open
6556 | Features and functionalities on the work order screen | Implementation | Select Medical - Implementation | Features and functionalities on the work order screen | open
6555 | Training to Agents | Implementation | Select Medical - Implementation | Training to Agents | open
6554 | Tasking responsibility detailed report extraction and interpretation | Implementation | Select Medical - Implementation | Tasking responsibility detailed report extraction and interpretation | open
6553 | Tasking summary report extraction and interpretation | Implementation | Select Medical - Implementation | Tasking summary report extraction and interpretation | open
6552 | Billing Production reports extraction and interpretation | Implementation | Select Medical - Implementation | Billing Production reports extraction and interpretation | open
6551 | Activity and production reports extraction and interpretation | Implementation | Select Medical - Implementation | Activity and production reports extraction and interpretation | open
6550 | Tasks approval
6549 | Tasking allocation and return task allocation | Implementation | Select Medical - Implementation | Tasking allocation and return task allocation | open
6548 | Managing team leaders own workorder | Implementation | Select Medical - Implementation | Managing team leaders own workorder | open
6547 | Managing teams workorder | Implementation | Select Medical - Implementation | Managing teams workorder | open
6546 | Auto and Manual Tasks allocation
inventory" | open
6545 | Auto and Manual encounters allocation
deallocation of inventory" | open
6544 | Training to Team Leaders | Implementation | Select Medical - Implementation | Training to Team Leaders | open
6543 | DARE Summary report extraction and interpretation | Implementation | Select Medical - Implementation | DARE Summary report extraction and interpretation | open
6542 | how to perform Operations Shuffling | Implementation | Select Medical - Implementation | how to perform Operations Shuffling | open
6541 | Interpretation of the Outstanding report | Implementation | Select Medical - Implementation | Interpretation of the Outstanding report | open
6540 | The exceptions considered while preparing the AR Operations strategy | Implementation | Select Medical - Implementation | The exceptions considered while preparing the AR Operations strategy | open
6539 | The AR non-workable logics setup in Optimix | Implementation | Select Medical - Implementation | The AR non-workable logics setup in Optimix | open
6538 | Tasking workflow set-up for CBO | Implementation | Select Medical - Implementation | Tasking workflow set-up for CBO | open
6537 | Current tasking workflow setup for Internal entities | Implementation | Select Medical - Implementation | Current tasking workflow setup for Internal entities | open
6536 | Current Operations strategy and rules set-up for billing workable inventory | Implementation | Select Medical - Implementation | Current Operations strategy and rules set-up for billing workable
inventory" | open
6535 | Current Operations strategy and the AR workable inventory rules set-up and the process to follow in | Implementation | Select Medical - Implementation | Current Operations strategy and the AR workable inventory rules set-up
and the process to follow in case of changing the rules set" | open
6534 | Training to Managers | Implementation | Select Medical - Implementation | Training to Managers | open
6533 | Training Schedule to be prepared and calendar invites sent to Select users | Implementation | Select Medical - Implementation | Training Schedule to be prepared and calendar invites sent to Select
users" | open
6532 | Make the necessary infrastructure arrangements if required for the trainings to be conducted | Implementation | Select Medical - Implementation | Make the necessary infrastructure arrangements if required for the
trainings to be conducted" | open
6531 | Plan the mode of training for the 2 CBO users | Implementation | Select Medical - Implementation | Plan the mode of training for the 2 CBO users | open
6530 | Plan the mode of training to be given to the clinic users | Implementation | Select Medical - Implementation | Plan the mode of training to be given to the clinic users | open
6529 | Training plan drafted clearly calling out the modules
of training and place of training" | open
6528 | Training Plan and Scheduling | Implementation | Select Medical - Implementation | Training Plan and Scheduling | open
6527 | Looking in to individual hourly production | Implementation | Select Medical - Implementation | Looking in to individual hourly production | open
6526 | Working on rejected tasks from a supervisor | Implementation | Select Medical - Implementation | Working on rejected tasks from a supervisor | open
6525 | Working on incoming tasks inventory | Implementation | Select Medical - Implementation | Working on incoming tasks inventory | open
6524 | Tasking from an encounter
6523 | Completing an encounter/ task | Implementation | Select Medical - Implementation | Completing an encounter/ task | open
6522 | Forwarding an encounter/ task | Implementation | Select Medical - Implementation | Forwarding an encounter/ task | open
6521 | Features and functionalities on the work order screen | Implementation | Select Medical - Implementation | Features and functionalities on the work order screen | open
6520 | To Perform Agents Activities | Implementation | Select Medical - Implementation | To Perform Agents Activities | open
6519 | Tasking responsibility detailed report extraction and interpretation | Implementation | Select Medical - Implementation | Tasking responsibility detailed report extraction and interpretation | open
6518 | Tasking summary report extraction and interpretation | Implementation | Select Medical - Implementation | Tasking summary report extraction and interpretation | open
6517 | Rejection production reports extraction and interpretation | Implementation | Select Medical - Implementation | Rejection production reports extraction and interpretation | open
6516 | Activity and production reports extraction and interpretation | Implementation | Select Medical - Implementation | Activity and production reports extraction and interpretation | open
6515 | Tasks approval
6514 | Tasking allocation and return task allocation | Implementation | Select Medical - Implementation | Tasking allocation and return task allocation | open
6513 | Managing team leaders own workorder | Implementation | Select Medical - Implementation | Managing team leaders own workorder | open
6512 | Managing teams workorder | Implementation | Select Medical - Implementation | Managing teams workorder | open
6511 | Auto and Manual Tasks allocation
inventory" | open
6510 | Auto and Manual encounters allocation
deallocation of inventory" | open
6509 | To Perform Team Leader Activities | Implementation | Select Medical - Implementation | To Perform Team Leader Activities | open
6508 | DARE Summary report extraction and interpretation | Implementation | Select Medical - Implementation | DARE Summary report extraction and interpretation | open
6507 | how to perform Operations Shuffling | Implementation | Select Medical - Implementation | how to perform Operations Shuffling | open
6506 | Interpretation of the Outstanding report | Implementation | Select Medical - Implementation | Interpretation of the Outstanding report | open
6505 | The exceptions considered while preparing the AR Operations strategy | Implementation | Select Medical - Implementation | The exceptions considered while preparing the AR Operations strategy | open
6504 | The AR non-workable logics setup in Optimix | Implementation | Select Medical - Implementation | The AR non-workable logics setup in Optimix | open
6503 | Tasking workflow set-up for CBO | Implementation | Select Medical - Implementation | Tasking workflow set-up for CBO | open
6502 | Current tasking workflow setup for Internal entities | Implementation | Select Medical - Implementation | Current tasking workflow setup for Internal entities | open
6501 | Current Operations strategy and rules set-up for billing workable inventory | Implementation | Select Medical - Implementation | Current Operations strategy and rules set-up for billing workable
inventory" | open
6500 | Current Operations strategy and the AR workable inventory rules set-up and the process to follow in | Implementation | Select Medical - Implementation | Current Operations strategy and the AR workable inventory rules set-up
and the process to follow in case of changing the rules set" | open
6499 | Perform Administration/ Manager Activities | Implementation | Select Medical - Implementation | Perform Administration/ Manager Activities | open
6498 | Give an Overall working demo on the product | Implementation | Select Medical - Implementation | Give an Overall working demo on the product | open
6497 | Select trainer creates availability based on the schedule | Implementation | Select Medical - Implementation | Select trainer creates availability based on the schedule | open
6496 | Training Schedule to be prepared and calendar invites sent to Select users | Implementation | Select Medical - Implementation | Training Schedule to be prepared and calendar invites sent to Select
users" | open
6495 | Training plan drafted clearly with the sessions and topics to be trained on which day
trained on which day
6494 | Plan for Training | Implementation | Select Medical - Implementation | Plan for Training | open
6493 | Masters Validation | Implementation | Select Medical - Implementation | Masters Validation | open
6492 | User Mapping validation | Implementation | Select Medical - Implementation | User Mapping validation | open
6491 | Buckets Mapping validation | Implementation | Select Medical - Implementation | Buckets Mapping validation | open
6490 | Bucket validation | Implementation | Select Medical - Implementation | Bucket validation | open
6489 | Rules Logic Validation | Implementation | Select Medical - Implementation | Rules Logic Validation | open
6488 | Rules Logic Validation | Implementation | Select Medical - Implementation | Rules Logic Validation | open
6487 | OS report validation | Implementation | Select Medical - Implementation | OS report validation | open
6486 | OS Vs Ageing validation | Implementation | Select Medical - Implementation | OS Vs Ageing validation | open
6485 | Validation | Implementation | Select Medical - Implementation | Validation | open
6484 | User Mapping configuration - Clinics | Implementation | Select Medical - Implementation | User Mapping configuration - Clinics | open
6483 | Tasking Buckets Mapping configuration - Clinics | Implementation | Select Medical - Implementation | Tasking Buckets Mapping configuration - Clinics | open
6482 | Creation of Tasking Buckets - Clinics | Implementation | Select Medical - Implementation | Creation of Tasking Buckets - Clinics | open
6481 | User Mapping configuration - Other Entities | Implementation | Select Medical - Implementation | User Mapping configuration - Other Entities | open
6480 | Tasking Buckets Mapping configuration - Other Entities | Implementation | Select Medical - Implementation | Tasking Buckets Mapping configuration - Other Entities | open
6479 | Creation of Tasking Buckets - Other Entities | Implementation | Select Medical - Implementation | Creation of Tasking Buckets - Other Entities | open
6478 | User Mapping configuration - PP | Implementation | Select Medical - Implementation | User Mapping configuration - PP | open
6477 | Tasking Buckets Mapping configuration - PP | Implementation | Select Medical - Implementation | Tasking Buckets Mapping configuration - PP | open
6476 | Creation of Tasking Buckets - PP | Implementation | Select Medical - Implementation | Creation of Tasking Buckets - PP | open
6475 | User Mapping configuration - Rejection Management | Implementation | Select Medical - Implementation | User Mapping configuration - Rejection Management | open
6474 | Buckets Mapping configuration - Rejection Management | Implementation | Select Medical - Implementation | Buckets Mapping configuration - Rejection Management | open
6473 | Creation of rules - Rejection Management | Implementation | Select Medical - Implementation | Creation of rules - Rejection Management | open
6472 | Creation of Buckets - Rejection Management | Implementation | Select Medical - Implementation | Creation of Buckets - Rejection Management | open
6471 | User Mapping configuration - AR | Implementation | Select Medical - Implementation | User Mapping configuration - AR | open
6470 | Buckets Mapping configuration - AR | Implementation | Select Medical - Implementation | Buckets Mapping configuration - AR | open
6469 | Creation of rules - AR | Implementation | Select Medical - Implementation | Creation of rules - AR | open
6468 | Creation of Buckets - AR | Implementation | Select Medical - Implementation | Creation of Buckets - AR | open
6467 | User Masters upload | Implementation | Select Medical - Implementation | User Masters upload | open
6466 | Masters Data Configuration | Implementation | Select Medical - Implementation | Masters Data Configuration | open
6465 | Clinics Mapping: Location/Practice/Bucket | Implementation | Select Medical - Implementation | Clinics Mapping: Location/Practice/Bucket | open
6464 | Tasking Buckets Mapping to Users - AR / Billing / PP / Other Entities | Implementation | Select Medical - Implementation | Tasking Buckets Mapping to Users - AR / Billing / PP / Other Entities | open
6463 | Buckets Mapping to Users - AR / Billing / PP / Other Entities | Implementation | Select Medical - Implementation | Buckets Mapping to Users - AR / Billing / PP / Other Entities | open
6462 | User Master - AR / Billing / PP / Other Entities | Implementation | Select Medical - Implementation | User Master - AR / Billing / PP / Other Entities | open
6461 | Rejections Bucket Masters | Implementation | Select Medical - Implementation | Rejections Bucket Masters | open
6460 | Rejection Messages Groupings | Implementation | Select Medical - Implementation | Rejection Messages Groupings | open
6459 | Rules Masters - Rejections | Implementation | Select Medical - Implementation | Rules Masters - Rejections | open
6458 | Rules Masters - AR | Implementation | Select Medical - Implementation | Rules Masters - AR | open
6457 | Denial Categorization groupings | Implementation | Select Medical - Implementation | Denial Categorization groupings | open
6456 | Buckets Master | Implementation | Select Medical - Implementation | Buckets Master | open
6455 | Payer AFL Details | Implementation | Select Medical - Implementation | Payer AFL Details | open
6454 | Payer TFL Details | Implementation | Select Medical - Implementation | Payer TFL Details | open
6453 | Action Codes | Implementation | Select Medical - Implementation | Action Codes | open
6452 | Status Codes | Implementation | Select Medical - Implementation | Status Codes | open
6451 | AR Groupings (Specialty/Payers wise / FC's / Service Lines) | Implementation | Select Medical - Implementation | AR Groupings (Specialty/Payers wise / FC's / Service Lines) | open
6450 | Templates to be shared with Select Process Owners | Implementation | Select Medical - Implementation | Templates to be shared with Select Process Owners | open
6449 | Implementation consultant to validate the template to ensure masters are as expected | Implementation | Select Medical - Implementation | Implementation consultant to validate the template to ensure masters
are as expected" | open
6448 | Select Medical process owners to share the filled Masters with Implementation Team | Implementation | Select Medical - Implementation | Select Medical process owners to share the filled Masters with
Implementation Team" | open
6447 | Select Medical process owners to fill the data in the given template | Implementation | Select Medical - Implementation | Select Medical process owners to fill the data in the given template | open
6446 | Explain the template(s) to Select Medical process owners | Implementation | Select Medical - Implementation | Explain the template(s) to Select Medical process owners | open
6445 | Share the master template(s) with Select Team process owners | Implementation | Select Medical - Implementation | Share the master template(s) with Select Team process owners | open
6444 | Masters Data Collections Template Share | Implementation | Select Medical - Implementation | Masters Data Collections Template Share | open
6443 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6442 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6441 | Define Clinics In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define Clinics In-Coming task buckets responsibility | open
6440 | Define Clinics In-Coming tasks and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Define Clinics In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6439 | Design Clinics out-going tasks and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Design Clinics out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6438 | Detailed explanation to the Implementation process consultant on the agreed standard Operations proc | Implementation | Select Medical - Implementation | Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners" | open
6437 | Process Fitment - Clinics Tasking Process Design | Implementation | Select Medical - Implementation | Process Fitment - Clinics Tasking Process Design | open
6436 | Incase of discrepancy revert back to the Select and close the gap | Implementation | Select Medical - Implementation | Incase of discrepancy revert back to the Select and close the gap | open
6435 | Validate configuration
6434 | Provide required IT Infrastructure
6433 | Explain the infrastructure requirement to Select IT | Implementation | Select Medical - Implementation | Explain the infrastructure requirement to Select IT | open
6432 | Prepare the IT infrastructure requirement specification document and share the same with Select IT | Implementation | Select Medical - Implementation | Prepare the IT infrastructure requirement specification document and
share the same with Select IT" | open
6431 | Understand the type/size of business and define the infrastructure requirement | Implementation | Select Medical - Implementation | Understand the type/size of business and define the infrastructure
requirement" | open
6430 | Identify IT point of contact to coordinate with IKS technical implementation team | Implementation | Select Medical - Implementation | Identify IT point of contact to coordinate with IKS technical
implementation team" | open
6429 | Infrastructure Requirement | Implementation | Select Medical - Implementation | Infrastructure Requirement | open
6424 | Travel ticket and the required documentations are prepared and shared with the Optimix Implementatio | Implementation | Select Medical - Implementation | Travel ticket and the required documentations are prepared and shared
with the Optimix Implementation team" | open
6423 | Booking of Flight tickets for travel of Implementation team | Implementation | Select Medical - Implementation | Booking of Flight tickets for travel of Implementation team | open
6422 | Select medical provides the necessary approval on the travel plan | Implementation | Select Medical - Implementation | Select medical provides the necessary approval on the travel plan | open
6421 | Share the travel plan Select for approval on the Implementation resource travel | Implementation | Select Medical - Implementation | Share the travel plan Select for approval on the Implementation
resource travel" | open
6420 | Prepare the travel plan for IKS implementation resources to travel onsite to accomplish key Implemen | Implementation | Select Medical - Implementation | Prepare the travel plan for IKS implementation resources to travel
onsite to accomplish key Implementation activities" | open
6419 | Implementation Team Travel Plan | Implementation | Select Medical - Implementation | Implementation Team Travel Plan | open
6418 | SOW Sign-Off by Select Medical | Implementation | Select Medical - Implementation | SOW Sign-Off by Select Medical | open
6417 | Finalized SOW copy sent to the relevant stake holders for Sign-off | Implementation | Select Medical - Implementation | Finalized SOW copy sent to the relevant stake holders for Sign-off | open
6416 | Select confirms on the SOW to IKS | Implementation | Select Medical - Implementation | Select confirms on the SOW to IKS | open
6415 | Make amendments / Changes
from Select" | open
6414 | Select Medical reviews the SOW and send back to IKS | Implementation | Select Medical - Implementation | Select Medical reviews the SOW and send back to IKS | open
6413 | Prepare SOW and shares the same with Select Medical | Implementation | Select Medical - Implementation | Prepare SOW and shares the same with Select Medical | open
6411 | Detailed explanation to the Implementation process consultant on the agreed standard Operations proc | Implementation | Select Medical - Implementation | Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners" | open
6410 | Design Clinics out-going tasks and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Design Clinics out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6409 | Define Other entities team In-Coming tasks and buckets based on the agreed standard process between | Implementation | Select Medical - Implementation | Define Other entities team In-Coming tasks and buckets based on the
agreed standard process between PTA process owners and Select Process
Owners
" | open
6407 | Statement of Work | Implementation | Select Medical - Implementation | Statement ofWork | open
6406 | Share the project plan with all the stake holders post confirmation from Select | Implementation | Select Medical - Implementation | Share the project plan with all the stake holders post confirmation
from Select
" | open
6404 | Approval on the project plan | Implementation | Select Medical - Implementation | Approval on the project plan | open
6403 | Make the changes
Select" | open
6402 | Discuss for any changes on the dates and the resources to be point of contact for each process from | Implementation | Select Medical - Implementation | Discuss for any changes on the dates and the resources to be point of
contact for each process from Select and resource to be the project
manager from Select" | open
6401 | Share and explain the project plan in the scheduled call | Implementation | Select Medical - Implementation | Share and explain the project plan in the scheduled call | open
6400 | Check for Select leadership availability for a scheduled call | Implementation | Select Medical - Implementation | Check for Select leadership availability for a scheduled call | open
6399 | Kick-Off call with Select Medical | Implementation | Select Medical - Implementation | Kick-Off call with Select Medical | open
6370 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6369 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6368 | Define rejection team In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define rejection team In-Coming task buckets responsibility | open
6367 | Define rejection team In-Coming tasks and buckets based on the agreed standard process between PTA p | Implementation | Select Medical - Implementation | Define rejection team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6366 | Design rejection team out-going tasks and buckets based on the agreed standard process between PTA p | Implementation | Select Medical - Implementation | Design rejection team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6365 | Sign-off on the Optimix to-be process document | Implementation | Select Medical - Implementation | Sign-off on the Optimix to-be process document | open
6364 | Document the Optimix to-be Rejections workflow management process based on the agreed standard proce | Implementation | Select Medical - Implementation | Document the Optimix to-be Rejections workflow management process
based on the agreed standard process between PTA process owners and
Select Process Owners" | open
6360 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6359 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6358 | Define Other entities team In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define Other entities team In-Coming task buckets responsibility | open
6354 | Process Fitment - Other Entity Tasking Process Design | Implementation | Select Medical - Implementation | Process Fitment - Other Entity Tasking Process Design | open
6353 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6352 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6351 | Define PP team In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define PP team In-Coming task buckets responsibility | open
6350 | Define PP team In-Coming tasks and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Define PP team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6349 | Design PP team out-going tasks and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Design PP team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6348 | Detailed explanation to the Implementation process consultant on the agreed standard Operations proc | Implementation | Select Medical - Implementation | Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners" | open
6347 | Process Fitment - PP Tasking Process Design | Implementation | Select Medical - Implementation | Process Fitment - PP Tasking Process Design | open
6346 | Sign-Off on the rules and buckets | Implementation | Select Medical - Implementation | Sign-Off on the rules and buckets | open
6345 | Document the rules & buckets | Implementation | Select Medical - Implementation | Document the rules & buckets | open
6344 | Design PAR/RA Rules & Buckets | Implementation | Select Medical - Implementation | Design PAR/RA Rules & Buckets | open
6343 | CSR AS-IS strategy discussion | Implementation | Select Medical - Implementation | CSR AS-IS strategy discussion | open
6342 | RA AS-IS Strategy discussion | Implementation | Select Medical - Implementation | RA AS-IS Strategy discussion | open
6341 | PAR AS-IS Strategy discussion | Implementation | Select Medical - Implementation | PAR AS-IS Strategy discussion | open
6340 | Process Fitment - PAR / CSR Operations Strategy and Tasking workflow Design | Implementation | Select Medical - Implementation | Process Fitment - PAR / CSR Operations Strategy and Tasking workflow
Design" | open
6339 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6338 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6337 | Define rejection team In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define rejection team In-Coming task buckets responsibility | open
6336 | Define rejection team In-Coming tasks and buckets based on the agreed standard process between PTA p | Implementation | Select Medical - Implementation | Define rejection team In-Coming tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6335 | Design rejection team out-going tasks and buckets based on the agreed standard process between PTA p | Implementation | Select Medical - Implementation | Design rejection team out-going tasks and buckets based on the agreed
standard process between PTA process owners and Select Process Owners" | open
6334 | Sign-off on the Optimix to-be process document | Implementation | Select Medical - Implementation | Sign-off on the Optimix to-be process document | open
6333 | Document the Optimix to-be Rejections workflow management process based on the agreed standard proce | Implementation | Select Medical - Implementation | Document the Optimix to-be Rejections workflow management process
based on the agreed standard process between PTA process owners and
Select Process Owners" | open
6331 | Perform Gap Analysis to identify any Gaps between Optimix process and the designed standard Strategy | Implementation | Select Medical - Implementation | Perform Gap Analysis to identify any Gaps between Optimix process and
the designed standard Strategy" | open
6330 | Design the Operations team Hierarchy based on the agreed standard process between PTA process owners | Implementation | Select Medical - Implementation | Design the Operations team Hierarchy based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6329 | Design rejections workable inventory rules logics and buckets based on the agreed standard process b | Implementation | Select Medical - Implementation | Design rejections workable inventory rules logics and buckets based on
the agreed standard process between PTA process owners and Select
Process Owners" | open
6328 | Design Exceptional logics based on the agreed standard process between PTA process owners and Select | Implementation | Select Medical - Implementation | Design Exceptional logics based on the agreed standard process between
PTA process owners and Select Process Owners" | open
6327 | Design Exclusion rules logics and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Design Exclusion rules logics and buckets based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6326 | Design Rejection Groupings based on the agreed standard process between PTA process owners and Selec | Implementation | Select Medical - Implementation | Design Rejection Groupings based on the agreed standard process
between PTA process owners and Select Process Owners" | open
6325 | Detailed explanation to the Implementation process consultant on the agreed standard Operations proc | Implementation | Select Medical - Implementation | Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners" | open
6324 | Process Fitment - Rejections Operation Strategy and Tasking Process Design | Implementation | Select Medical - Implementation | Process Fitment - Rejections Operation Strategy and Tasking Process
Design" | open
6323 | Sign-off on the defined Optimix to-be tasking process | Implementation | Select Medical - Implementation | Sign-off on the defined Optimix to-be tasking process | open
6322 | Design the standard tasking buckets and document the tasking work flow process | Implementation | Select Medical - Implementation | Design the standard tasking buckets and document the tasking work flow
process" | open
6321 | Define AR In-Coming task buckets responsibility | Implementation | Select Medical - Implementation | Define AR In-Coming task buckets responsibility | open
6320 | Define AR In-Coming tasks and buckets based on the agreed standard process between PTA process owner | Implementation | Select Medical - Implementation | Define AR In-Coming tasks and buckets based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6319 | Design AR Out-Going tasks and buckets based on the agreed standard process between PTA process owner | Implementation | Select Medical - Implementation | Design AR Out-Going tasks and buckets based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6318 | Sign-off on the Optimix to-be process document | Implementation | Select Medical - Implementation | Sign-off on the Optimix to-be process document | open
6317 | Document the Optimix to-be AR & Denial Operations workflow management process based on the agreed s | Implementation | Select Medical - Implementation | Document the Optimix to-be AR & Denial Operations workflow management
process based on the agreed standard process between PTA process
owners and Select Process Owners" | open
6316 | Perform Gap Analysis to identify any Gaps between Optimix process and the designed standard Strategy | Implementation | Select Medical - Implementation | Perform Gap Analysis to identify any Gaps between Optimix process and
the designed standard Strategy" | open
6315 | Design the Operations team Hierarchy based on the agreed standard process between PTA process owners | Implementation | Select Medical - Implementation | Design the Operations team Hierarchy based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6314 | Design AR and Denial workable inventory rules logics and buckets based on the agreed standard proces | Implementation | Select Medical - Implementation | Design AR and Denial workable inventory rules logics and buckets based
on the agreed standard process between PTA process owners and Select
Process Owners" | open
6313 | Design Exceptional logics based on the agreed standard process between PTA process owners and Select | Implementation | Select Medical - Implementation | Design Exceptional logics based on the agreed standard process between
PTA process owners and Select Process Owners" | open
6312 | Design Exclusion rules logics and buckets based on the agreed standard process between PTA process | Implementation | Select Medical - Implementation | Design Exclusion rules logics and buckets based on the agreed standard
process between PTA process owners and Select Process Owners" | open
6311 | Design External Groupings (Payers/FC/Location/Denials/Clinic) based on the agreed standard process b | Implementation | Select Medical - Implementation | Design External Groupings (Payers/FC/Location/Denials/Clinic) based on
the agreed standard process between PTA process owners and Select
Process Owners" | open
6310 | Detailed explanation to the Implementation process consultant on the agreed standard Operations proc | Implementation | Select Medical - Implementation | Detailed explanation to the Implementation process consultant on the
agreed standard Operations process between PTA process owners and
Select Process Owners" | open
6309 | Process Fitment - AR/Denial Operation Strategy and Tasking Process Design | Implementation | Select Medical - Implementation | Process Fitment - AR/Denial Operation Strategy and Tasking Process
Design" | open
6308 | Sign-off on the agreed process flow | Implementation | Select Medical - Implementation | Sign-off on the agreed process flow | open
6307 | Document the finalized Clinic tasking workflow process across PTA and select Medical Operations | Implementation | Select Medical - Implementation | Document the finalized Clinic tasking workflow process across PTA and
select Medical Operations" | open
6306 | Standardization of the Clinic tasking workflow process between PTA and Select Medical | Implementation | Select Medical - Implementation | Standardization of the Clinic tasking workflow process between PTA and
Select Medical" | open
6305 | Discuss the Current Clinic tasking workflow process between PTA and Select Medical Process owners | Implementation | Select Medical - Implementation | Discuss the Current Clinic tasking workflow process between PTA and
Select Medical Process owners" | open
6304 | Sign-off on the agreed process flow | Implementation | Select Medical - Implementation | Sign-off on the agreed process flow | open
6302 | Document the finalized Other Entity tasking workflow process across PTA and select Medical Operation | Implementation | Select Medical - Implementation | Document the finalized Other Entity tasking workflow process across
PTA and select Medical Operations" | open
6301 | Standardization of the Other Entity tasking workflow process between PTA and Select Medical | Implementation | Select Medical - Implementation | Standardization of the Other Entity tasking workflow process between
PTA and Select Medical" | open
6300 | Discuss the Current Other Entity tasking workflow process between PTA and Select Medical Process own | Implementation | Select Medical - Implementation | Discuss the Current Other Entity tasking workflow process between PTA
and Select Medical Process owners" | open
6299 | Sign-off on the agreed process flow | Implementation | Select Medical - Implementation | Sign-off on the agreed process flow | open
6298 | Document the finalized rejection management workflow process across PTA and select Medical Operation | Implementation | Select Medical - Implementation | Document the finalized rejection management workflow process across
PTA and select Medical Operations" | open
6297 | Standardization of the Rejection Management Workflow process between PTA and Select Medical | Implementation | Select Medical - Implementation | Standardization of the Rejection Management Workflow process between
PTA and Select Medical" | open
6296 | Discuss the Current Rejections handling process workflow between PTA and Select Medical Process owne | Implementation | Select Medical - Implementation | Discuss the Current Rejections handling process workflow between PTA
and Select Medical Process owners" | open
6295 | Sign-off on the agreed process flow | Implementation | Select Medical - Implementation | Sign-off on the agreed process flow | open
6294 | Document the finalized rejection management workflow process across PTA and select Medical Operation | Implementation | Select Medical - Implementation | Document the finalized rejection management workflow process across
PTA and select Medical Operations" | open
6293 | Standardization of the Rejection Management Workflow process between PTA and Select Medical | Implementation | Select Medical - Implementation | Standardization of the Rejection Management Workflow process between
PTA and Select Medical" | open
6292 | Discuss the Current Rejections handling process workflow between PTA and Select Medical Process owne | Implementation | Select Medical - Implementation | Discuss the Current Rejections handling process workflow between PTA
and Select Medical Process owners" | open
6291 | Sign-off on the agreed process flow | Implementation | Select Medical - Implementation | Sign-off on the agreed process flow | open
6290 | Document the finalized standard workflow process across PTA and select Medical Operations | Implementation | Select Medical - Implementation | Document the finalized standard workflow process across PTA and select
Medical Operations" | open
6289 | Standardization of the AR workflow process between PTA and Select Medical | Implementation | Select Medical - Implementation | Standardization of the AR workflow process between PTA and Select
Medical" | open
6288 | Discuss on the Current AR Operations workflow process of PTA and Select Medical | Implementation | Select Medical - Implementation | Discuss on the Current AR Operations workflow process of PTA and
Select Medical" | open
6287 | Operations Process Fitment - PTA/Select Workflow Calibration | Implementation | Select Medical - Implementation | Operations Process Fitment - PTA/Select Workflow Calibration | open
6286 | Final Sign-off on the understanding of the scope for Optimix Implementation | Implementation | Select Medical - Implementation | Final Sign-off on the understanding of the scope for Optimix
Implementation" | open
6285 | Optimix Implementation team reviews and understand the scope document and come up with questions if | Implementation | Select Medical - Implementation | Optimix Implementation team reviews and understand the scope document
and come up with questions if any for clarification" | open
6284 | Revert back the filled in scope document to Optimix Implementation team for the team review and scop | Implementation | Select Medical - Implementation | Revert back the filled in scope document to Optimix Implementation
team for the team review and scope understanding" | open
6283 | Fill in the Scope document with the relevant information | Implementation | Select Medical - Implementation | Fill in the Scope document with the relevant information | open
6282 | Share the Scope document template with the Select Project Manager | Implementation | Select Medical - Implementation | Share the Scope document template with the Select Project Manager | open
6281 | Initiate the Optimix Scope discussion with the respective Select Project Manager | Implementation | Select Medical - Implementation | Initiate the Optimix Scope discussion with the respective Select
Project Manager" | open
6280 | Address CBO teams and introduce the implementation team | Implementation | Select Medical - Implementation | Address CBO teams and introduce the implementation team | open
6279 | Scope | Implementation | Select Medical - Implementation | Scope | open
6278 | Validate the monitoring process | Implementation | Select Medical - Implementation | Validate the monitoring process | open
6277 | Design the process flow which will call out the time of file placement
placement
execution and monitoring phase" | open
6276 | Test the scripts /data feed files in the UAT server | Implementation | Select Medical - Implementation | Test the scripts /data feed files in the UAT server | open
6275 | Deploy the scripts/data feed files in the UAT server | Implementation | Select Medical - Implementation | Deploy the scripts/data feed files in the UAT server | open
6274 | Develop scripts /data feed files as specified by IKS Implementation tech team | Implementation | Select Medical - Implementation | Develop scripts /data feed files as specified by IKS Implementation
tech team" | open
6273 | Send the required data set list to the client IT team and get the required data set | Implementation | Select Medical - Implementation | Send the required data set list to the client IT team and get the
required data set" | open
6256 | Data Extraction from RT | Implementation | Select Medical - Implementation | Data Extraction from RT | open
6255 | Access from the Clinic machines and check if the user is able to access the application from Clinics | Implementation | Select Medical - Implementation | Access from the Clinic machines and check if the user is able to
access the application from Clinics" | open
6254 | Access from the node machines and check if the user is able to access the application from CBO's | Implementation | Select Medical - Implementation | Access from the node machines and check if the user is able to access
the application from CBO's" | open
6253 | Validated that the basic Configurations/Entities are available as expected | Implementation | Select Medical - Implementation | Validated that the basic Configurations/Entities are available as
expected" | open
6252 | Deploy Optimix Application in the Production environment | Implementation | Select Medical - Implementation | Deploy Optimix Application in the Production environment | open
6251 | Deploy Optimix Application in the UAT environment | Implementation | Select Medical - Implementation | Deploy Optimix Application in the UAT environment | open
6250 | Optimix Configuration | Implementation | Select Medical - Implementation | Optimix Configuration | open